## Project Budget
IBP Corp Green Diesel and African Palm Project | [11 empty] | 100.3% | 99.5% | 102% | 97%
Project Budget |  | # de la activity | activities precedents | sequences, activities what continuant after de terminated this activity | Expected value in Euros | initiates de responsible | start date of activity | End date | duration days | optimistic duration days | pessimistic duration days | worst case scenario | best case scenario
|  | AG, AD, EF, JS, JCH | 3500000
USES OF FUNDS |  | JXS, JS, AD, CP, JCH | 1500000
Future And Owed Financial Expenses | Financial expenses, commissions and owed retainers | AG, AD, EF, JS, JCH | 7500000 |  | 5500000 | AG, CT, EY, JS, JCH,FA,DC,MT,EY | 2014-04-20 | 2014-04-30 | 10 | 7 | 12 | 5516500 | 5472500
Pre-Expense | Paid out Capital | JXS, JS, AD, CP, JCH | 1500000 |  | 3500000 | GD1, VAG, CT, PC, JCH,FA,EY | 2014-04-20 | 2014-04-30 | 10 | 7 | 12 | 3510500 | 3482500
| Auditing, Accounting, Legal & Miscellaneous | JXS, JS, AD | 1580000 | 4,6 | 1580000 | AG,DC,DCM,FA,PC,RBA,CEP,LA,MT,EY | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 1584740 | 1572100
Expence | Unforeseen expenses | RB, PB, VM, DB, AD, JCH | 2000000 |  | 2000000 | AG,DC,DCM,FA,PC,RBA,CEP,LA,MT,EY,LA | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 2006000 | 1990000
Expense | Labor and Salaries for the first 4 years & IBP payroll bank trust Account | AG, SC, DCM, MTP, SP, JCH | 20000000 |  | 20000000 | AG,RBA, DB, VM, CT, JCH,RD,PC,FA,MT,EY | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 20060000 | 19900000
Purchase | Office Quito and Panama and Eurpe | AD, JCH, JXS, HE, GE | 1800000 |  | 1800000 | RBA, DB, VM, CT, JCH,RD,PC,FA,MT,EY | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 1805400 | 1791000
Purchase | Security & Surveillance Systems | AD, JCH, JXS, HE, GE | 3530000 |  | 530000 | GA1,CEP,MT,XF | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 531590 | 527350
Purchase | Corporate, Fire, Flood, & Liability Insurance, Performance Bond | HE, PB, VM, SC | 450000 | 7,12 | 450000 | AG, SC, DCM, FT, SP, JCH,PC,RD,FA,GASL1 | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 451350 | 447750
Expense | Contingency plan in Bank IBP Trust Account | EF, JS, AD, AG, JCH | 5500000 |  | 5500000 | AG, JCH, BM1,BM2, GE,FT,CEP,MT | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 5516500 | 5472500
Purchase | Furniture, Fixtures, & Equipment | HE, VM, SC, JXS, MTP | 200000 |  | 200000 | XF,JCH,LA,KL,VAG,CEP,VM,FT,MT,GASL1 | 2012-04-20 | 2012-04-30 | 10 | 7 | 12 | 200600 | 199000
Purchase | Purchase of 3080 (+/-) hectares for Industrial installations for African palm fruit process and extraction and refining oil and installation cost. | GE, HE, VM, PB | 3240000 |  | 7240000 | VM, SC, RD | 2012-04-20 | 2012-07-19 | 90 | 60 | 120 | 7384800 | 7022800
Purchase | Purchase of 42 thousand (+/-) hectares to build Pools for the growing of Sea Algae, extraction plant for oil and Green Diesel refinery | AG, HE, VM, PB, JCH, EF, CP | 8695000 |  | 8695000 | VM, RD, CT, AG, JCH,AL,MT,GASL1 | 2012-06-20 | 2013-04-16 | 300 | 270 | 365 | 8868900 | 8434150
Operational Expense | All Permits, | AG, HE, GE, AD, JCH, EF, DCM, CP | 1500000 |  | 1500000 | GE,AG,FT,BM1,BM2,MT, | 2012-06-20 | 2013-05-16 | 330 | 270 | 365 | 1530000 | 1455000
Opertional Expense | Property maintenance - cleaning of jungle weeds, wild vegetation, shrubbery | HE, AM, GE, VM, PB, RB, DC, JXS | 2465000 |  | 465000 | GE, FT,DC, FA, MT | 2012-06-20 | 2013-12-12 | 540 | 365 | 600 | 474300 | 451050
Purchase | Micro Turbines 1.5 Kw/H | AG, HE, CP, AD, JS, AM, EF, DCM | 4700000 |  | 4700000 | AG,FT, VM, PB, JCH, EF, CEP | 2012-08-20 | 2013-08-20 | 365 | 300 | 540 | 4794000 | 4559000
Purchase | Vegetable Oil production plant for Sea Algae with 3 expellers o produce a minimum of 15 thousand Gallons oil per Hct /Day | AG, HE, GE, DC, CP, AD, EF, JXS | 25200000 |  | 25200000 | AG, RD, GE,CT, JCH, SP, DCM, CEP,FT,MT | 2012-08-20 | 2012-12-18 | 120 | 90 | 180 | 25704000 | 24444000
Purchase | Bio Diesel production plant conversion equipment and refinery & NAFTA Refinery | HE, GE, JXS, DC, SC, VM, JCH | 200000000 |  | 230000000 | RD, AG, GE, VM, RBA, DC, VAG, GASL1 | 2012-08-20 | 2012-09-19 | 30 | 15 | 60 | 234600000 | 223100000
Construction Expence | Septic Tanks for 40 Hectares with leach lines included and construction of pools on of 15 Thousand Hectares for growing Sea Algae | HE, GE, JXS, DC, SC, JCH, CP | 5500000 |  | 1000000 | AG, RD, CT, FA, JCH, AM, VM, DCM | 2012-09-20 | 2012-10-20 | 30 | 30 | 90 | 1020000 | 970000
Construction Expense | Chemical Recuperation Pools | GE, HE, AG, DC, JXS, JCH | 112658 |  | 112658 | AG, RD, GE, DC, CEP, AD, EF, GA1 | 2012-09-20 | 2012-10-20 | 30 | 30 | 90 | 114911.16 | 109278.26
Investment Purchase | Purchase of African Palm Fruit | JS, AD, HE, JXS, JCH | 8500036 |  | 4500036 | RD, GE, VAG, DC, SC, VM, CEP,FT,MT,GA1 | 2012-10-20 | 2013-10-20 | 365 | 300 | 540 | 4590036.72 | 4365034.92
Purchase | Purchase of African Palm 500.000 plants | PC, AD, EF, AM, PB, MT | 2500000 |  | 2500000 | RD, GE, DC, SC, JCH, GA1,MT,VM | 2012-11-20 | 2013-11-20 | 365 | 300 | 450 | 2550000 | 2425000
Purchase | Purchase Sea Algae genetic matirial for 50 million gallons year | AD, JS, JXS, HE | 2000000 |  | 2000000 | GE, RD, AG, DC, GA1, JCH,MT,FT,BM3 | 2012-11-20 | 2013-05-19 | 180 | 120 | 450 | 2040000 | 1940000
Purchase And Construction Expense | 10Harvesting Boats for Sea Algae and harvesting & recollection docks for Sea Algae. | PC, HE, GE, AD, JXS | 1200000 |  | 1200000 | CEP, AG, RD,MT, JCH,FT,BM4 | 2012-11-20 | 2013-11-20 | 365 | 120 | 450 | 1224000 | 1164000
Construction Expense | Stationary Irrigation System and water drain channels | PC, HE, EF, MT | 5500000 |  | 1500000 | GA1, AG, CT, MT, FT,JCH,FA,GASL1 | 2012-11-20 | 2013-03-20 | 120 | 90 | 180 | 1530000 | 1455000
Construction Expence | Septic Tanks for 40 Acres with leach lines Santa Elena | JCH, AD, HE, PB, MT | 248000 |  | 248000 | AG,VAG,GA1, RD,MT | 2012-11-20 | 2013-03-20 | 120 | 90 | 180 | 252960 | 240560
Construction Expense | Ocean Cargo Boat Loading Dock and floating peer | PC, HE, EF, DC | 6000000 |  | 4000000 | RD, CEP, GE, AG, GA1 | 2012-11-20 | 2013-07-18 | 240 | 180 | 330 | 4080000 | 3880000
Purchase | Vehicles, harvesting equipment such as Haul Tractors, Harvest Baskets, Construction of Harvest Gathering and Warehousing, (8 tractors, 10 trucks) | RB, DCM, JS, AG | 2743426 |  | 2743426 | CEP, RD, FA,RBA,DB,AL, MT,GASL1,EY,FT | 2012-12-20 | 2014-06-13 | 540 | 450 | 720 | 2798294.52 | 2661123.22
Purchase | 2 Land movement Tractors & 1 Rear excavator equipment And two bulldozers with rear excavators | MTP, MT, PC, DC, VM | 1000000 |  | 1000000 | JCH, AG, CT, MT,FT,CEP | 2012-12-20 | 2013-05-29 | 160 | 120 | 180 | 1020000 | 970000
Construction Expense | Construction of office site Infrastructure in San Lorenzo and Santa Elena | MT, MTP, VM, AG, HE, GE | 468598.4 |  | 468598.4 | CEP, GE, FA, DCM,KL,AL,SP,SY,DCM | 2012-12-20 | 2014-03-15 | 450 | 365 | 270 | 477970.368 | 454540.448
Construction Expense | Housing for employees Santa Elena / San Lorenzo | MTP, VM, MT, DC, AM, DCM | 2000000 |  | 2000000 | RB, DCM, VAG, AG,VM,FT | 2013-01-20 | 2013-11-16 | 300 | 80 | 365 | 2040000 | 1940000
Construction Expence | Septic Tanks for 10 hectares with leach lines included and pools San Lorenzo | AD, AG, JS, EF, RB, DCM, JCH | 1000000 |  | 1000000 | FT, MT, CEP, DCM, VM,CEP | 2013-03-20 | 2013-03-30 | 10 | 7 | 12 | 1020000 | 970000
Construction Expense | School, Medical center, Food Distribution Center and Church (Santa Elena $2.000.000 and San Lorenzo $1.000.000) | AD,. AG, JS, HE, GE, EF | 3000000 |  | 1500000 | MT, FT, VM, AG, RD, GE,PC,EY | 2013-05-20 | 2014-03-16 | 300 | 80 | 270 | 1530000 | 1455000
Constuction Expence | Power and Phone Line installation | AD, AG, JCH, RB, JXS | 3062281 |  | 1062281 | FT, VM, MT, DC, AG, DCM,CEP,EY | 2013-05-20 | 2013-07-19 | 60 | 30 | 90 | 1083526.62 | 1030412.57
Construction Expence | Electricity & Fuel for 2 Years | AD, JCH, AG, JXS, JS | 150000 |  | 150000 | AG,CT,FA,JCH | 2013-05-20 | 2013-05-30 | 10 | 7 | 12 | 153000 | 145500
Construcion Expense | Storage tanks in Ecuador at property for the Vegetable Oil and Bio Diesel and Storage Tanks at Port site for Bio Diesel to be exported. extracted oil and bio Diesel | AG, AD, JCH, JS, EF, DC | 4000000 |  | 4000000
Expence | Associated Research & Development with USA and European Universities |  | 23100000 |  | 3100000
Expence | Sea Water Tax |  | 55000 |  | 35000
| TOTAL INVESTMENT |  |  |  | 352979999.4 | 0 |  |  |  | 3839 | 7029 | 352063879.388 | 336496149.418
| Required Investment |  |  |  | 353000000
Formulas:
End date = [start date of activity]+[duration days]

## AfricanPalm Project Budget
IBP Corp Green Diesel and African Palm Project
Project Budget |  | Expected value in Euros
USES OF FUNDS
Future And Owed Financial Expenses | Financial expenses, commissions and owed retainers | 5500000
Pre-Expense | Paid out Capital | 3500000
| Auditing, Accounting, Legal & Miscellaneous | 1580000
Expense | Unforeseen expenses | 2000000
Expense | Labor and Salaries for the first 4 years & IBP payroll bank trust Account | 20000000
Purchase | Office Quito and Panama and Europe | 1800000
Purchase | Security & Surveillance Systems | 530000
Purchase | Corporate, Fire, Flood, & Liability Insurance, Performance Bond | 450000
Expense | Contingency plan in Bank IBP Trust Account | 5500000
Purchase | Furniture, Fixtures, & Equipment | 200000
Purchase | Purchase of 3080 (+/-) hectares for Industrial installations for African palm fruit process and extraction and refining oil and installation cost. | 7240000
Purchase | Purchase of 42 thousand (+/-) hectares to build Pools for the growing of Sea Algae, extraction plant for oil and Green Diesel refinery | 8695000 | 42000
Operational Expense | All Permits, | 1500000
Operational Expense | Property maintenance - cleaning of jungle weeds, wild vegetation, shrubbery | 465000
Purchase | Micro Turbines 1.5 Kw/H | 4700000
Purchase | Vegetable Oil production plant for Sea Algae with 3 expellers to produce a minimum of 15 thousand Gallons oil per Hct /Day | 25200000 | 0
Purchase | Bio Diesel production plant conversion equipment and refinery & Naphta Refinery | 230000000
Construction Expense | Septic Tanks for 40 Hectares with leach lines included and construction of pools on of 15 Thousand Hectares for growing Sea Algae | 1000000
Construction Expense | Chemical Recuperation Pools | 112658
Investment Purchase | Purchase of African Palm Fruit | 4500036
Purchase | Purchase of African Palm 500.000 plants | 2500000
Purchase | Purchase Sea Algae genetic material for 50 million gallons year | 2000000
Purchase And Construction Expense | 10 Harvesting Boats for Sea Algae and harvesting & recollection docks for Sea Algae. | 1200000
Construction Expense | Stationary Irrigation System and water drain channels | 1500000
Construction Expense | Septic Tanks for 40 Acres with leach lines Santa Elena | 248000
Construction Expense | Ocean Cargo Boat Loading Dock and floating peer | 4000000
Purchase | Vehicles, harvesting equipment such as Haul Tractors, Harvest Baskets, Construction of Harvest Gathering and Warehousing, (8 tractors, 10 trucks) | 2743426
Purchase | 2 Land movement Tractors & 1 Rear excavator equipment And two bulldozers with rear excavators | 1000000
Construction Expense | Construction of office site Infrastructure in San Lorenzo and Santa Elena | 468598.4
Construction Expense | Housing for employees Santa Elena / San Lorenzo | 2000000
Construction Expense | Septic Tanks for 10 hectares with leach lines included and pools San Lorenzo | 1000000
Construction Expense | School, Medical center, Food Distribution Center and Church (Santa Elena $2.000.000 and San Lorenzo $1.000.000) | 1500000
Construction Expense | Power and Phone Line installation | 1062281
Construction Expense | Electricity & Fuel for 2 Years | 150000
Construction Expense | Storage tanks in Ecuador at property for the Vegetable Oil and Bio Diesel and Storage Tanks at Port site for Bio Diesel to be exported. extracted oil and bio Diesel | 4000000
Expense | Associated Research & Development with USA and European Universities | 3100000
Expense | Sea Water Tax | 35000
| TOTAL INVESTMENT | 352979999.4
| Required Investment | 353000000

## AfricanPalm Project Budget - 2
| IBP Corp Green Diesel and African Palm Project | [12 empty] | 1.003 | 0.995 | 102% | 97%
| Project Budget |  | # de la activity | activities precedents | sequences, activities what continuant after de terminated this activity | Potential Suppliers | Expected value in Euros | initiates de responsible | start date of activity | End date | duration days | optimistic duration days | pessimistic duration days | worst case scenario | best case scenario
|  |  | AG, AD, EF, JS, JCH | 3500000
| USES OF FUNDS |  | JXS, JS, AD, CP, JCH | 1500000
| Future And Owed Financial Expenses | Financial expenses, commissions and owed retainers | AG, AD, EF, JS, JCH | 7500000 |  | IBP Corp | 5500000 | AG, CT, EY, JS, JCH,FA,DC,MT,EY | 2014-04-20 | 2014-04-30 | 10 | 7 | 12 | 5516500 | 5472500
| Pre-Expense | Paid out Capital | JXS, JS, AD, CP, JCH | 1500000 |  | IBP Corp | 3500000 | GD1, VAG, CT, PC, JCH,FA,EY | 2014-04-20 | 2014-04-30 | 10 | 7 | 12 | 3510500 | 3482500
|  | Auditing, Accounting, Legal & Miscellaneous | JXS, JS, AD | 1580000 | 4,6 | IBP Corp | 1580000 | AG,DC,DCM,FA,PC,RBA,CEP,LA,MT,EY | 2014-04-04 | 2014-04-14 | 10 | 7 | 12 | 1584740 | 1572100
| Expense | Unforeseen expenses | RB, PB, VM, DB, AD, JCH | 2000000 |  | IBP Corp | 2000000 | AG,DC,DCM,FA,PC,RBA,CEP,LA,MT,EY,LA | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 2006000 | 1990000
| Expense | Labor and Salaries for the first 4 years & IBP payroll bank trust Account | AG, SC, DCM, MTP, SP, JCH | 20000000 |  | IBP Corp | 20000000 | AG,RBA, DB, VM, CT, JCH,RD,PC,FA,MT,EY | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 20060000 | 19900000
| Purchase | Office Quito and Panama and Europe | AD, JCH, JXS, HE, GE | 1800000 |  | IBP Corp | 1800000 | RBA, DB, VM, CT, JCH,RD,PC,FA,MT,EY | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 1805400 | 1791000
| Purchase | Security & Surveillance Systems | AD, JCH, JXS, HE, GE | 3530000 |  | Local Supply | 530000 | GA1,CEP,MT,XF | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 531590 | 527350
| Purchase | Corporate, Fire, Flood, & Liability Insurance, Performance Bond | HE, PB, VM, SC | 450000 | 7,12 | IBP Corp | 450000 | AG, SC, DCM, FT, SP, JCH,PC,RD,FA,GASL1 | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 451350 | 447750
| Expense | Contingency plan in Bank IBP Trust Account | EF, JS, AD, AG, JCH | 5500000 |  | IBP Corp | 5500000 | AG, JCH, BM1,BM2, GE,FT,CEP,MT | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 5516500 | 5472500
| Purchase | Furniture, Fixtures, & Equipment | HE, VM, SC, JXS, MTP | 200000 |  | Local Supply | 200000 | XF,JCH,LA,KL,VAG,CEP,VM,FT,MT,GASL1 | 2013-04-20 | 2013-04-30 | 10 | 7 | 12 | 200600 | 199000
2350.6494 | Purchase | Purchase of 3080 (+/-) hectares for Industrial installations for African palm fruit process and extraction and refining oil and installation cost. | GE, HE, VM, PB | 3240000 |  | IBP Corp | 7240000 | VM, SC, RD | 2013-04-20 | 2013-07-19 | 90 | 60 | 120 | 7384800 | 7022800
207.0238 | Purchase | Purchase of 42 thousand (+/-) hectares to build Pools for the growing of Sea Algae, extraction plant for oil and Green Diesel refinery | AG, HE, VM, PB, JCH, EF, CP | 8695000 |  | IBP Corp | 8695000 | VM, RD, CT, AG, JCH,AL,MT,GASL1 | 2013-06-20 | 2014-04-16 | 300 | 270 | 365 | 8868900 | 8434150
| Operational Expense | All Permits, | AG, HE, GE, AD, JCH, EF, DCM, CP | 1500000 |  | URS Corporation | 1500000 | GE,AG,FT,BM1,BM2,MT, | 2013-06-20 | 2014-05-16 | 330 | 270 | 365 | 1530000 | 1455000
| Operational Expense | Property maintenance - cleaning of jungle weeds, wild vegetation, shrubbery | HE, AM, GE, VM, PB, RB, DC, JXS | 2465000 |  | Local Labor | 465000 | GE, FT,DC, FA, MT | 2013-06-20 | 2014-12-12 | 540 | 365 | 600 | 474300 | 451050
| Purchase | Micro Turbines 1.5 Kw/H | AG, HE, CP, AD, JS, AM, EF, DCM | 4700000 |  | Capstone Turbine Corporation | 4700000 | AG,FT, VM, PB, JCH, EF, CEP | 2013-08-20 | 2014-08-20 | 365 | 300 | 540 | 4794000 | 4559000
| Purchase | Vegetable Oil production plant for Sea Algae with extraction to produce a minimum of 50,000,000 Gallons oil per Year | AG, HE, GE, DC, CP, AD, EF, JXS | 25200000 |  | Sapphire Energy, Inc. | 25200000 | AG, RD, GE,CT, JCH, SP, DCM, CEP,FT,MT | 2013-08-20 | 2013-12-18 | 120 | 90 | 180 | 25704000 | 24444000
| Purchase | Renewable Diesel production plant conversion equipment and refinery & Naphtha Refinery | HE, GE, JXS, DC, SC, VM, JCH | 200000000 |  | Next Step Energy, Inc. URS Corporation | 230000000 | RD, AG, GE, VM, RBA, DC, VAG, GASL1 | 2013-08-20 | 2013-09-19 | 30 | 15 | 60 | 234600000 | 223100000
| Construction Expense | Septic Tanks for 40 Hectares with leach lines included and construction of pools on of 15 Thousand Hectares for growing Sea Algae | HE, GE, JXS, DC, SC, JCH, CP | 5500000 |  | Local | 1000000 | AG, RD, CT, FA, JCH, AM, VM, DCM | 2013-09-20 | 2013-10-20 | 30 | 30 | 90 | 1020000 | 970000
| Construction Expense | Chemical Recuperation Pools | GE, HE, AG, DC, JXS, JCH | 112658 |  | Local | 112658 | AG, RD, GE, DC, CEP, AD, EF, GA1 | 2013-09-20 | 2013-10-20 | 30 | 30 | 90 | 114911.16 | 109278.26
| Investment Purchase | Purchase of African Palm Fruit | JS, AD, HE, JXS, JCH | 8500036 |  |  | 4500036 | RD, GE, VAG, DC, SC, VM, CEP,FT,MT,GA1 | 2013-10-20 | 2014-10-20 | 365 | 300 | 540 | 4590036.72 | 4365034.92
| Purchase | Purchase of African Palm 500.000 plants | PC, AD, EF, AM, PB, MT | 2500000 |  |  | 2500000 | RD, GE, DC, SC, JCH, GA1,MT,VM | 2013-11-20 | 2014-11-20 | 365 | 300 | 450 | 2550000 | 2425000
| Purchase | Purchase Sea Algae genetic material for 50 million gallons year | AD, JS, JXS, HE | 2000000 |  | Sapphire Energy, Inc. | 2000000 | GE, RD, AG, DC, GA1, JCH,MT,FT,BM3 | 2013-11-20 | 2014-05-19 | 180 | 120 | 450 | 2040000 | 1940000
| Purchase And Construction Expense | 10 Harvesting Boats for Sea Algae and harvesting & recollection docks for Sea Algae. | PC, HE, GE, AD, JXS | 1200000 |  | JCM International Group, Inc. | 1200000 | CEP, AG, RD,MT, JCH,FT,BM4 | 2013-11-20 | 2014-11-20 | 365 | 120 | 450 | 1224000 | 1164000
| Construction Expense | Stationary Irrigation System and water drain channels | PC, HE, EF, MT | 5500000 |  | JCM International Group, Inc. | 1500000 | GA1, AG, CT, MT, FT,JCH,FA,GASL1 | 2013-11-20 | 2014-03-20 | 120 | 90 | 180 | 1530000 | 1455000
| Construction Expense | Septic Tanks for 40 Acres with leach lines Santa Elena | JCH, AD, HE, PB, MT | 248000 |  | Local Fabrication and Installation | 248000 | AG,VAG,GA1, RD,MT | 2013-11-20 | 2014-03-20 | 120 | 90 | 180 | 252960 | 240560
| Construction Expense | Ocean Cargo Boat Loading Dock and floating peer | PC, HE, EF, DC | 6000000 |  | URS Corporation | 4000000 | RD, CEP, GE, AG, GA1 | 2013-11-20 | 2014-07-18 | 240 | 180 | 330 | 4080000 | 3880000
| Purchase | Vehicles, harvesting equipment such as Haul Tractors, Harvest Baskets, Construction of Harvest Gathering and Warehousing, (8 tractors, 10 trucks) | RB, DCM, JS, AG | 2743426 |  | JCM International Group, Inc. | 2743426 | CEP, RD, FA,RBA,DB,AL, MT,GASL1,EY,FT | 2013-11-20 | 2015-05-14 | 540 | 450 | 720 | 2798294.52 | 2661123.22
| Purchase | 2 Land movement Tractors & 1 Rear excavator equipment And two bulldozers with rear excavators | MTP, MT, PC, DC, VM | 1000000 |  | JCM International Group, Inc. | 1000000 | JCH, AG, CT, MT,FT,CEP | 2013-11-20 | 2014-04-29 | 160 | 120 | 180 | 1020000 | 970000
| Construction Expense | Construction of office site Infrastructure in San Lorenzo and Santa Elena | MT, MTP, VM, AG, HE, GE | 468598.4 |  | Local design and construction | 468598.4 | CEP, GE, FA, DCM,KL,AL,SP,SY,DCM | 2013-12-20 | 2015-03-15 | 450 | 365 | 270 | 477970.368 | 454540.448
| Construction Expense | Housing for employees Santa Elena / San Lorenzo | MTP, VM, MT, DC, AM, DCM | 2000000 |  | Local design and construction | 2000000 | RB, DCM, VAG, AG,VM,FT | 2014-01-20 | 2014-11-16 | 300 | 80 | 365 | 2040000 | 1940000
| Construction Expense | Septic Tanks for 10 hectares with leach lines included and pools San Lorenzo | AD, AG, JS, EF, RB, DCM, JCH | 1000000 |  | Local design and construction | 1000000 | FT, MT, CEP, DCM, VM,CEP | 2014-03-20 | 2014-03-30 | 10 | 7 | 12 | 1020000 | 970000
| Construction Expense | School, Medical center, Food Distribution Center and Church (Santa Elena $2.000.000 and San Lorenzo $1.000.000) | AD,. AG, JS, HE, GE, EF | 3000000 |  | Local design and construction | 1500000 | MT, FT, VM, AG, RD, GE,PC,EY | 2014-05-20 | 2015-03-16 | 300 | 80 | 270 | 1530000 | 1455000
| Construction Expense | Power and Phone Line installation | AD, AG, JCH, RB, JXS | 3062281 |  | Local Utility | 1062281 | FT, VM, MT, DC, AG, DCM,CEP,EY | 2014-05-20 | 2014-07-19 | 60 | 30 | 90 | 1083526.62 | 1030412.57
| Construction Expense | Electricity & Fuel for 2 Years | AD, JCH, AG, JXS, JS | 150000 |  | Local Utility | 150000 | AG,CT,FA,JCH | 2014-05-20 | 2014-05-30 | 10 | 7 | 12 | 153000 | 145500
| Construction Expense | Storage tanks in Ecuador at property for the Vegetable Oil and Bio Diesel and Storage Tanks at Port site for Bio Diesel to be exported. extracted oil and bio Diesel | AG, AD, JCH, JS, EF, DC | 4000000 |  | Local Fabrication and Installation | 4000000
| Expense | Associated Research & Development with USA and European Universities |  | 23100000 |  | IBP Corp | 3100000
| Expense | Sea Water Tax |  | 55000 |  | IBP Corp | 35000
|  | TOTAL INVESTMENT |  |  |  |  | 352979999.4 | 0 |  |  |  | 3839 | 7029 | 352063879.388 | 336496149.418
|  | Required Investment |  |  |  |  | 353000000
Formulas:
End date = [start date of activity]+[duration days]

## Complete financial Gantt
IBP CORP FINANCIAL GANTT
[14 empty] | AÑO 1 | [11 empty] | AÑO 2 | [11 empty] | AÑO 3 | [11 empty] | AÑO 4 | [11 empty] | AÑO 5 | [11 empty] | AÑO 6 | [11 empty] | AÑO 7 | [11 empty] | AÑO 8 | [11 empty] | AÑO 9 | [11 empty] | AÑO 10
IBP CORP. FINANCIAL GANTT |  | initial |  |  |  | initial | duration days | duration optimist | duration expected | duration pessimist | pessimist used | optimist USD | fin | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22 | Month 23 | Month 24 | Month 25 | Month 26 | Month 27 | Month 28 | Month 29 | Month 30 | Month 31 | Month 32 | Month 33 | Month 34 | Month 35 | Month 36 | Month 37 | Month 38 | Month 39 | Month 40 | Month 41 | Month 42 | Month 43 | Month 44 | Month 45 | Month 46 | Month 47 | Month 48 | Month 49 | Month 50 | Month 51 | Month 52 | Month 53 | Month 54 | Month 55 | Month 56 | Month 57 | Month 58 | Month 59 | Month 60 | Month 61 | Month 62 | Month 63 | Month 64 | Month 65 | Month 66 | Month 67 | Month 68 | Month 69 | Month 70 | Month 71 | Month 72 | Month 73 | Month 74 | Month 75 | Month 76 | Month 77 | Month 78 | Month 79 | Month 80 | Month 81 | Month 82 | Month 83 | Month 84 | Month 85 | Month 86 | Month 87 | Month 88 | Month 89 | Month 90 | Month 91 | Month 92 | Month 93 | Month 94 | Month 95 | Month 96 | Month 97 | Month 98 | Month 99 | Month 100 | Month 101 | Month 102 | Month 103 | Month 104 | Month 105 | Month 106 | Month 107 | Month 108 | Month 109 | Month 110 | Month 111 | Month 112 | Month 113 | Month 114 | Month 115 | Month 116 | Month 117 | Month 118 | Month 119 | Month 120
|  |  |  | diferencial cambiario | Up to 10 Years for repayment
USES OF FUNDS
| Financial expenses, commissions and owed retainers | AG, AD, EF, JS, JCH | 5500000 | 1.3 | 7150000 | 39923 | 57 | 55 | 57 | 60 |  |  | 39934.7361 | 7150000
| Paid out Capital | JXS, JS, AD, CP, JCH | 3500000 | 1.3 | 4550000 | 39923 | [6 empty] | 39934.7361 | 4550000
| Auditing, Accounting, Legal & Miscellaneous | JXS, JS, AD | 1580000 | 1.3 | 2054000 | 39923 | [6 empty] | 39934.7361 | 2054000
| Unforeseen expenses | RB, PB, VM, DB, AD, JCH | 2000000 | 1.3 | 2600000 | 39923 | [6 empty] | 39934.7361 | 2600000
| Labor and Salaries for the first 4 years & IBP payroll bank trust Account | AG, SC, DCM, MTP, SP, JCH | 20000000 | 1.3 | 26000000 | 39923 | [6 empty] | 39934.7361 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667 | 541666.6667
| Office Quito and Panama and Italia | AD, JCH, JXS, HE, GE | 1800000 | 1.3 | 2340000 | 39923 | [6 empty] | 39934.7361 | 2340000
| Security & Surveillance Systems | AD, JCH, JXS, HE, GE | 530000 | 1.3 | 689000 | 39923 | [6 empty] | 39934.7361 | 689000
| Corporate, Fire, Flood, & Liability Insurance, Performance Bond | HE, PB, VM, SC | 450000 | 1.3 | 585000 | 39923 | [6 empty] | 39934.7361 | 585000
| Contingency plan in Bank IBP Trust Account | EF, JS, AD, AG, JCH | 5500000 | 1.3 | 7150000 | 39923 | [6 empty] | 39934.7361 | 7150000
| Furniture, Fixtures, & Equipment | HE, VM, SC, JXS, MTP | 200000 | 1.3 | 260000 | 39923 | [6 empty] | 39948.6806 |  | 260000
| Purchase of 3080 (+/-) hectares for Industrial installations for African palm fruit process and extraction and refining oil and installation cost. | GE, HE, VM, PB | 7240000 | 1.3 | 10000000 | 39923 | [6 empty] | 39934.7361 | 10000000
| Purchase of 42 thousand (+/-) hectares to build Pools for the growing of Sea Algae, extraction plant for oil and Green Diesel refinery | AG, HE, VM, PB, JCH, EF, CP | 8695000 | 1.3 | 11303500 | 39923 | [6 empty] | 39934.7361 | 11303500
| All Permits, | AG, HE, GE, AD, JCH, EF, DCM, CP | 1500000 | 1.3 | 1950000 | 39923 | [6 empty] | 39934.7361 | 1950000
| Property maintenance - cleaning of jungle weeds, wild vegetation, shrubbery | HE, AM, GE, VM, PB, RB, DC, JXS | 465000 | 1.3 | 604500 | 39923 | [6 empty] | 40060.7361 | 120900 | 120900 | 120900 | 120900 | 120900
| Micro Turbines 1.5 Kw/H | AG, HE, CP, AD, JS, AM, EF, DCM | 4700000 | 1.3 | 6110000 | 39984 | [6 empty] | 40490.6806 |  |  | 4888000 | [16 empty] | 1222000
| Vegetable Oil production plant for Sea Algae with 3 expellers o produce a minimum of 15 thousand Gallons oil per Hct /Day | AG, HE, GE, DC, CP, AD, EF, JXS | 25200000 | 1.3 | 32760000 | 39984 | [6 empty] | 40518.6806 |  |  | 26208000 | [17 empty] | 6552000
| Bio Diesel production plant conversion equipment and refinery & NAFTA Refinery | HE, GE, JXS, DC, SC, VM, JCH | 230000000 | 1.3 | 299000000 | 39984 | [6 empty] | 40791.6806 |  |  | 239200000 | [26 empty] | 59800000
| Septic Tanks for 40 Hectares with leach lines included and construction of pools on of 15 Thousand Hectares for growing Sea Algae | HE, GE, JXS, DC, SC, JCH, CP | 1000000 | 1.3 | 1300000 | 40045 | [6 empty] | 40598.4306 |  |  |  |  | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526 | 68421.0526
| Chemical Recuperation Pools | GE, HE, AG, DC, JXS, JCH | 112658 | 1.3 | 146455.4 | 40045 | [6 empty] | 40235.7361 |  |  |  |  | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789 | 7708.1789
| Purchase of African Palm Fruit | JS, AD, HE, JXS, JCH | 4500036 | 1.3 | 5850046.8 | 40045 | [6 empty] | 40107.4861 | [5 empty] | 2925023.4 | 2925023.4
| Purchase of African Palm 500.000 plants | PC, AD, EF, AM, PB, MT | 2500000 | 1.3 | 3250000 | 40076 | [6 empty] | 40130.7917 | [6 empty] | 1625000 | 1625000
| Purchase Sea Algae seed | AD, JS, JXS, HE | 2000000 | 1.3 | 2600000 | 40076 | [6 empty] | 40130.7917 | [6 empty] | 1300000 | 1300000
| 10Harvesting Boats for Sea Algae and harvesting & recollection docks for Sea Algae. | PC, HE, GE, AD, JXS | 1200000 | 1.3 | 1560000 | 40106 | [6 empty] | 40641.4861 | [7 empty] | 780000 |  |  |  | 780000
| Stationary Irrigation System and water drain channels | PC, HE, EF, MT | 1500000 | 1.3 | 1950000 | 40137 | [6 empty] | 40653.4861 | [8 empty] | 390000 | 390000 | 390000 | 390000 | 390000
| Septic Tanks for 40 Acres with leach lines Santa Elena | JCH, AD, HE, PB, MT | 248000 | 1.3 | 322400 | 40137 | [6 empty] | 40437.7917 | [8 empty] | 32240 | 32240 | 32240 | 32240 | 32240 | 32240 | 32240 | 32240 | 32240 | 32240 | [63 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ocean Cargo Boat Loading Dock and floating peer | PC, HE, EF, DC | 4000000 | 1.3 | 5200000 | 40137 | [6 empty] | 40611.4861 | [8 empty] | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667 | 346666.6667
| Vehicles, harvesting equipment such as Haul Tractors, Harvest Baskets, Construction of Harvest Gathering and Warehousing, (8 tractors, 10 trucks) | RB, DCM, JS, AG | 2743426 | 1.3 | 3566453.8 | 40137 | [6 empty] | 40158.7917 | [8 empty] | 3566453.8 | [72 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 Land movement Tractors & 1 Rear excavator equipment And two bulldozers with rear excavators | MTP, MT, PC, DC, VM | 1000000 | 1.3 | 1300000 | 40137 | [6 empty] | 40311.7917 | [8 empty] | 650000 |  |  |  | 650000
| Construction of office site Infrastructure in San Lorenzo and Santa Elena | MT, MTP, VM, AG, HE, GE | 468598.4 | 1.3 | 609177.92 | 40137 | [6 empty] | 40479.7917 | [8 empty] | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109 | 55379.8109
| Housing for employees Santa Elena / San Lorenzo | MTP, VM, MT, DC, AM, DCM | 2000000 | 1.3 | 2600000 | 40167 | [6 empty] | 40942.7917 | [9 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
| Septic Tanks for 10 hectares with leach lines included and pools San Lorenzo | AD, AG, JS, EF, RB, DCM, JCH | 1000000 | 1.3 | 1300000 | 40167 | [6 empty] | 40386.6806 | [9 empty] | 185714.2857 | 185714.2857 | 185714.2857 | 185714.2857 | 185714.2857 | 185714.2857 | 185714.2857 | [65 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| School, Medical center, Food Distribution Center and Church (Santa Elena $2.000.000 and San Lorenzo $1.000.000) | AD,. AG, JS, HE, GE, EF | 1500000 | 1.3 | 1950000 | 40167 | [6 empty] | 40735.7361 | [9 empty] | 278571.4286 | 278571.4286 | 278571.4286 | 278571.4286 | 278571.4286 | 278571.4286 | 278571.4286
| Power and Phone Line installation | AD, AG, JCH, RB, JXS | 1062281 | 1.3 | 1380965.3 | 40198 | [6 empty] | 40582.4306 | [10 empty] | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | 115080.4417 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Electricity & Fuel for 2 Years | AD, JCH, AG, JXS, JS | 150000 | 1.3 | 195000 | 40257 | [6 empty] | 41278.7917 | [12 empty] | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125 | 8125
| Storage tanks in Ecuador at property for the Vegetable Oil and Bio Diesel and Storage Tanks at Port site for Bio Diesel to be exported. extracted oil and bio Diesel | AG, AD, JCH, JS, EF, DC | 4000000 | 1.3 | 5200000 | 40318 | [6 empty] | 40680.4861 | [14 empty] | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | [66 empty] | 0 | [5 empty] | 0
| Associated Research & Development with USA and European Universities |  | 3100000 | 1.3 | 4030000 | 40318 | [6 empty] | 40401.7917 | [14 empty] | 2015000 | 2015000
| Sea Water Tax |  | 35000 | 1.3 | 45500 | 40318 | [6 empty] | 40331.7361 | [14 empty] | 45500
| Oil production cost | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989900 | 1989900 | 1989900 | 1989900 | 1989900 | 1989900 | 1989900 | 1989900 | 1989900 | 1989900 | 1999849.5 | 1999849.5 | 1999849.5 | 1999849.5 | 1999849.5 | 1999849.5 | 1999849.5 | 1999849.5 | 1999849.5 | 1999850.2325 | 1999850.9651 | 1999851.6976 | 2009851.6923 | 2009852.4285 | 2009853.1647 | 2009853.901 | 2009854.6372 | 2009855.3734 | 2009856.1096 | 2009856.8458 | 2009857.582 | 2009858.3182 | 2009859.0544 | 2009859.7906 | 2019909.8295 | 2019910.5694 | 2019911.3092 | 2019912.0491 | 2019912.789 | 2019913.5289 | 2019914.2688 | 2019915.0087 | 2019915.7486 | 2019916.4885 | 2019917.2284 | 2019917.9683 | 2030018.3017 | 2030019.0453 | 2030019.7889 | 2030020.5324 | 2030021.276 | 2030022.0196 | 2030022.7632 | 2030023.5068 | 2030024.2504 | 2030024.994 | 2030025.7376 | 2030026.4812 | 2040177.3609 | 2040178.1082 | 2040178.8555 | 2040179.6028 | 2040180.3501 | 2040181.0974 | 2040181.8447 | 2040182.592 | 2040183.3393 | 2040184.0866 | 2040184.8339 | 2040185.5812 | 2050387.2602 | 2050388.0112 | 2050388.7623 | 2050389.5133 | 2050390.2644 | 2050391.0154 | 2050391.7665 | 2050392.5175 | 2050393.2685 | 2050394.0196 | 2050394.7706 | 2050395.5217 | 2060648.2541 | 2060649.0089 | 2060649.7637 | 2060650.5185 | 2060651.2733 | 2060652.0281 | 2060652.7829 | 2060653.5377 | 2060654.2925 | 2060655.0473 | 2060655.8021 | 2060656.5569 | 2070960.5982 | 2070961.3568 | 2070962.1154 | 2070962.8739 | 2070963.6325 | 2070964.3911 | 2070965.1497 | 2070965.9082 | 2070966.6668 | 2070967.4254 | 2070968.1839 | 2070968.9425
| Nafta production cost | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8052884.6154 | 8052884.6154 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8093149.0385 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8133614.7837 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8174282.8576 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8215154.2719 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8256230.0432 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8297511.1934 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8338998.7494 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431 | 8380693.7431
| Biodiesel Production cost | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51768543.956 | 51768543.956 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52027386.6758 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52287523.6092 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52548961.2272 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 52811706.0334 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53075764.5636 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53341143.3864 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53607849.1033 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488 | 53875888.3488
Out going expenses Monthly Op. | [13 empty] | 51034066.6667 | 922566.6667 | 270958566.6667 | 662566.6667 | 738695.8982 | 3542819.2982 | 6467819.2982 | 4322795.8982 | 5658536.1758 | 2106368.0901 | 2221448.5318 | 3001448.5318 | 2879573.5318 | 1839573.5318 | 6323306.8651 | 6277806.8651 | 3798521.1508 | 3798521.1508 | 3766281.1508 | 4932901.3399 | 10262901.3399 | 3710901.3399 | 63217249.4697 | 62794453.5714 | 63103510.2143 | 63103510.2143 | 62670176.881 | 62670176.881 | 62670176.881 | 122470176.881 | 62670176.881 | 62670176.881 | 62670176.881 | 62670177.6135 | 62670178.346 | 62670179.0786 | 62972656.7519 | 62972657.4881 | 62972658.2243 | 62972658.9605 | 62972659.6967 | 62972660.4329 | 62972661.1691 | 62972661.9053 | 62972662.6415 | 62972663.3777 | 62972664.1139 | 62972664.8501 | 62743153.9143 | 62743154.6542 | 62743155.3941 | 62743156.134 | 62743156.8738 | 62743157.6137 | 62743158.3536 | 62743159.0935 | 62743159.8334 | 62743160.5733 | 62743161.3132 | 62743162.0531 | 63056878.6069 | 63056879.3505 | 63056880.0941 | 63056880.8377 | 63056881.5813 | 63056882.3249 | 63056883.0685 | 63056883.812 | 63056884.5556 | 63056885.2992 | 63056886.0428 | 63056886.7864 | 63372171.9676 | 63372172.7149 | 63372173.4623 | 63372174.2096 | 63372174.9569 | 63372175.7042 | 63372176.4515 | 63372177.1988 | 63372177.9461 | 63372178.6934 | 63372179.4407 | 63372180.188 | 63689041.84 | 63689042.591 | 63689043.3421 | 63689044.0931 | 63689044.8442 | 63689045.5952 | 63689046.3463 | 63689047.0973 | 63689047.8483 | 63689048.5994 | 63689049.3504 | 63689050.1015 | 64007496.1068 | 64007496.8616 | 64007497.6164 | 64007498.3712 | 64007499.126 | 64007499.8808 | 64007500.6356 | 64007501.3904 | 64007502.1452 | 64007502.9 | 64007503.6548 | 64007504.4096 | 64327542.6902 | 64327543.4488 | 64327544.2073 | 64327544.9659 | 64327545.7245 | 64327546.483 | 64327547.2416 | 64327548.0002 | 64327548.7588 | 64327549.5173 | 64327550.2759 | 64327551.0345
| Financial costs | [13 empty] | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47 | 2775165.47
Total Uses |  |  |  |  | 459461999.22 | [8 empty] | 51034066.6667 | 2672566.6667 | 272708566.6667 | 2412566.6667 | 2488695.8982 | 5292819.2982 | 8217819.2982 | 6072795.8982 | 7408536.1758 | 3856368.0901 | 3971448.5318 | 4751448.5318 | 4629573.5318 | 3589573.5318 | 8073306.8651 | 8027806.8651 | 5548521.1508 | 5548521.1508 | 5516281.1508 | 6682901.3399 | 12012901.3399 | 5460901.3399 | 64967249.4697 | 64544453.5714 | 64853510.2143 | 64853510.2143 | 64420176.881 | 64420176.881 | 64420176.881 | 124220176.881 | 64420176.881 | 64420176.881 | 64420176.881 | 64420177.6135 | 64420178.346 | 64420179.0786 | 64722656.7519 | 64722657.4881 | 64722658.2243 | 64722658.9605 | 64722659.6967 | 64722660.4329 | 64722661.1691 | 64722661.9053 | 64722662.6415 | 64722663.3777 | 64722664.1139 | 64722664.8501 | 64493153.9143 | 65518320.1242 | 65518320.8641 | 65518321.604 | 65518322.3438 | 65518323.0837 | 65518323.8236 | 65518324.5635 | 65518325.3034 | 65518326.0433 | 65518326.7832 | 65518327.5231 | 65832044.0769 | 65832044.8205 | 65832045.5641 | 65832046.3077 | 65832047.0513 | 65832047.7949 | 65832048.5385 | 65832049.282 | 65832050.0256 | 65832050.7692 | 65832051.5128 | 65832052.2564 | 66147337.4376 | 66147338.1849 | 66147338.9323 | 66147339.6796 | 66147340.4269 | 66147341.1742 | 66147341.9215 | 66147342.6688 | 66147343.4161 | 66147344.1634 | 66147344.9107 | 66147345.658 | 66464207.31 | 66464208.061 | 66464208.8121 | 66464209.5631 | 66464210.3142 | 66464211.0652 | 66464211.8163 | 66464212.5673 | 66464213.3183 | 66464214.0694 | 66464214.8204 | 66464215.5715 | 66782661.5768 | 66782662.3316 | 66782663.0864 | 66782663.8412 | 66782664.596 | 66782665.3508 | 66782666.1056 | 66782666.8604 | 66782667.6152 | 66782668.37 | 66782669.1248 | 66782669.8796 | 67102708.1602 | 67102708.9188 | 67102709.6773 | 67102710.4359 | 67102711.1945 | 67102711.953 | 67102712.7116 | 67102713.4702 | 67102714.2288 | 67102714.9873 | 67102715.7459 | 67102716.5045
459461999.22
Sources of Funds | Total Funds needed |  |  |  | 459461999.22
| Credit |  |  |  | 459461999.22 | [8 empty] | 459461999.22
| Sale of African palm oil | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4974750 | 4974750 | 4974750 | 4974750 | 4974750 | 4974750 | 4974750 | 4974750 | 4974750 | 4999623.75 | 4999623.75 | 4999623.75 | 4999623.75 | 4999623.75 | 4999623.75 | 4999623.75 | 4999623.75 | 4999623.75 | 4999625.5814 | 4999627.4127 | 4999629.2441 | 5024629.2308 | 5024631.0714 | 5024632.9119 | 5024634.7524 | 5024636.5929 | 5024638.4334 | 5024640.274 | 5024642.1145 | 5024643.955 | 5024645.7955 | 5024647.636 | 5024649.4766 | 5049774.5737 | 5049776.4234 | 5049778.2731 | 5049780.1228 | 5049781.9726 | 5049783.8223 | 5049785.672 | 5049787.5217 | 5049789.3715 | 5049791.2212 | 5049793.0709 | 5049794.9206 | 5075045.7542 | 5075047.6132 | 5075049.4721 | 5075051.3311 | 5075053.1901 | 5075055.0491 | 5075056.908 | 5075058.767 | 5075060.626 | 5075062.485 | 5075064.3439 | 5075066.2029 | 5100443.4022 | 5100445.2704 | 5100447.1387 | 5100449.007 | 5100450.8752 | 5100452.7435 | 5100454.6118 | 5100456.48 | 5100458.3483 | 5100460.2166 | 5100462.0848 | 5100463.9531 | 5125968.1505 | 5125970.0281 | 5125971.9057 | 5125973.7833 | 5125975.6609 | 5125977.5385 | 5125979.4161 | 5125981.2937 | 5125983.1714 | 5125985.049 | 5125986.9266 | 5125988.8042 | 5151620.6352 | 5151622.5222 | 5151624.4092 | 5151626.2962 | 5151628.1832 | 5151630.0702 | 5151631.9572 | 5151633.8442 | 5151635.7312 | 5151637.6182 | 5151639.5052 | 5151641.3922 | 5177401.4955 | 5177403.392 | 5177405.2884 | 5177407.1848 | 5177409.0813 | 5177410.9777 | 5177412.8741 | 5177414.7706 | 5177416.667 | 5177418.5634 | 5177420.4599 | 5177422.3563
| Sale of green diesel | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62122252.7473 | 62122252.7473 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62432864.011 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 62745028.331 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63058753.4727 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63374047.2401 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 63690917.4763 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64009372.0636 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64329418.924 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186 | 64651066.0186
| Sale of electricty to main grid | [24 empty] | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846 | 22115.3846
| Sale of Nafta | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11504120.8791 | 11504120.8791 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11561641.4835 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11619449.6909 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11677546.9394 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11735934.6741 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11794614.3475 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11853587.4192 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11912855.3563 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331 | 11972419.6331
Sale of CDF´s
| Minimal Financial Income |  |  |  | 0.05 | [20 empty] | 369059.5868 | 351399.5928 | 337999.3488 | 305861.0483 | 294506.5465 | 293435.0914 | 292359.1719 | 291413.1028 | 285602.1742 | 257558.7001 | 256698.3782 | 314667.9112 | 374640.6335 | 435213.0296 | 496037.8106 | 558921.5837 | 622067.3726 | 685476.269 | 499982.7024 | 562882.9126 | 626045.207 | 689470.6776 | 753160.4257 | 817115.5522 | 881337.163 | 946211.7591 | 1011356.6705 | 1076773.0237 | 1142461.9496 | 1208424.584 | 1274662.0673 | 1341175.5447 | 1407966.1662 | 1475035.0866 | 1542383.4654 | 1610012.467 | 1677923.2608 | 1748727.2596 | 1815554.7569 | 1882660.7067 | 1950046.2693 | 2017712.6097 | 2085660.8978 | 2153892.3084 | 2222408.0212 | 2291209.2207 | 2360297.0965 | 2429672.8431 | 2499337.6599 | 2569647.8126 | 2640250.9289 | 2711148.2294 | 2782340.9401 | 2853830.2916 | 2925617.5202 | 2997703.8668 | 3070090.5778 | 3142778.9048 | 3215770.1045 | 3289065.4388 | 3362666.175 | 3436930.4222 | 3511504.1086 | 3586388.5232 | 3661584.961 | 3737094.7219 | 3812919.1115 | 3889059.4407 | 3965517.0259 | 4042293.1891 | 4119389.2577 | 4196806.5645 | 4274546.4481 | 4352968.8738 | 4431718.0642 | 4510795.381 | 4590202.1913 | 4669939.868 | 4750009.7897 | 4830413.3407 | 4911151.9113 | 4992226.8973 | 5073639.7004 | 5155391.7282 | 5237484.3941 | 5320279.5321 | 5403419.6546 | 5486906.1989 | 5570740.6086 | 5654924.333 | 5739458.8276 | 5824345.5541 | 5909585.9799 | 5995181.5789 | 6081133.831 | 6167444.2221 | 6254114.2446 | 6341507.6139 | 6429265.1269 | 6517388.3009 | 6605878.6596 | 6694737.7329 | 6783967.057 | 6873568.1748 | 6963542.6352 | 7053891.994 | 7144617.8132 | 7235721.6614
Income operational Monthly | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391174.9714 | 373514.9774 | 360114.7334 | 5302726.4329 | 5291371.9311 | 5290300.476 | 5289224.5565 | 5288278.4874 | 5282467.5588 | 5254424.0847 | 78879937.3892 | 78937906.9222 | 79390885.2626 | 79451457.6587 | 79512282.4397 | 79575166.2129 | 79638312.0017 | 79701720.8981 | 79516227.3315 | 79579127.5417 | 79642289.8361 | 79705717.1381 | 79769408.7175 | 79833365.6754 | 80292559.8004 | 80357436.237 | 80422582.989 | 80488001.1827 | 80553691.9491 | 80619656.424 | 80685895.7479 | 80752411.0658 | 80819203.5278 | 80886274.2887 | 80953624.508 | 81021255.3502 | 81486113.6311 | 81556919.4797 | 81623748.8267 | 81690856.6263 | 81758244.0386 | 81825912.2287 | 81893862.3666 | 81962095.6269 | 82030613.1894 | 82099416.2386 | 82168505.9641 | 82237883.5605 | 82706480.7129 | 82776792.7245 | 82847397.6998 | 82918296.8593 | 82989491.4289 | 83060982.6395 | 83132771.727 | 83204859.9325 | 83277248.5026 | 83349938.6885 | 83422931.7472 | 83496228.9404 | 83970756.7855 | 84045022.901 | 84119598.4556 | 84194484.7386 | 84269683.0446 | 84345194.6737 | 84421020.9316 | 84497163.1291 | 84573622.5826 | 84650400.614 | 84727498.5509 | 84804917.726 | 85285589.4661 | 85364013.7693 | 85442764.8374 | 85521844.0318 | 85601252.7197 | 85680992.274 | 85761064.0733 | 85841469.5019 | 85922209.9501 | 86003286.8137 | 86084701.4944 | 86166455.3998 | 86653494.6942 | 86736291.7192 | 86819433.7286 | 86902922.16 | 86986758.4566 | 87070944.068 | 87155480.4497 | 87240369.0631 | 87325611.376 | 87411208.862 | 87497163.001 | 87583475.2792 | 88077116.7764 | 88164512.0421 | 88252271.4516 | 88340396.522 | 88428888.7772 | 88517749.7469 | 88606980.9674 | 88696583.9816 | 88786560.3385 | 88876911.5937 | 88967639.3093 | 89058745.054
Income operational Accumulates | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391174.9714 | 764689.9488 | 1124804.6823 | 6427531.1151 | 11718903.0462 | 17009203.5222 | 22298428.0787 | 27586706.5661 | 32869174.1249 | 38123598.2097 | 117003535.5989 | 195941442.5211 | 275332327.7838 | 354783785.4424 | 434296067.8821 | 513871234.095 | 593509546.0967 | 673211266.9948 | 752727494.3263 | 832306621.868 | 911948911.7041 | 991654628.8422 | 1071424037.5597 | 1151257403.2351 | 1231549963.0356 | 1311907399.2726 | 1392329982.2616 | 1472817983.4443 | 1553371675.3934 | 1633991331.8174 | 1714677227.5653 | 1795429638.6311 | 1876248842.1589 | 1957135116.4476 | 2038088740.9556 | 2119109996.3058 | 2200596109.9369 | 2282153029.4166 | 2363776778.2433 | 2445467634.8696 | 2527225878.9082 | 2609051791.1369 | 2690945653.5035 | 2772907749.1304 | 2854938362.3197 | 2937037778.5583 | 3019206284.5225 | 3101444168.0829 | 3184150648.7958 | 3266927441.5204 | 3349774839.2201 | 3432693136.0794 | 3515682627.5084 | 3598743610.1478 | 3681876381.8748 | 3765081241.8073 | 3848358490.3099 | 3931708428.9984 | 4015131360.7455 | 4098627589.686 | 4182598346.4714 | 4266643369.3725 | 4350762967.8281 | 4434957452.5666 | 4519227135.6112 | 4603572330.2849 | 4687993351.2165 | 4772490514.3456 | 4857064136.9281 | 4941714537.5422 | 5026442036.093 | 5111246953.819 | 5196532543.285 | 5281896557.0544 | 5367339321.8917 | 5452861165.9235 | 5538462418.6431 | 5624143410.9171 | 5709904474.9904 | 5795745944.4923 | 5881668154.4424 | 5967671441.2561 | 6053756142.7505 | 6139922598.1503 | 6226576092.8445 | 6313312384.5637 | 6400131818.2923 | 6487034740.4522 | 6574021498.9089 | 6661092442.9769 | 6748247923.4266 | 6835488292.4897 | 6922813903.8657 | 7010225112.7276 | 7097722275.7286 | 7185305751.0078 | 7273382867.7842 | 7361547379.8263 | 7449799651.2779 | 7538140047.7999 | 7626568936.5771 | 7715086686.324 | 7803693667.2914 | 7892390251.273 | 7981176811.6115 | 8070053723.2052 | 8159021362.5145 | 8248080107.5685
Net monthly cash flow | [13 empty] | -51034066.6667 | -2672566.6667 | -272708566.6667 | -2412566.6667 | -2488695.8982 | -5292819.2982 | -8217819.2982 | -6072795.8982 | -7408536.1758 | -3856368.0901 | -3971448.5318 | -4751448.5318 | -4238398.5604 | -3216058.5544 | -7713192.1317 | -2725080.4322 | -257149.2197 | -258220.6748 | -227056.5943 | -1394622.8525 | -6730433.7811 | -206477.2552 | 13912687.9195 | 14393453.3508 | 14537375.0484 | 14597947.4444 | 15092105.5587 | 15154989.3319 | 15218135.1208 | -44518455.9829 | 15096050.4505 | 15158950.6607 | 15222112.9552 | 15285539.5246 | 15349230.3715 | 15413186.5968 | 15569903.0486 | 15634778.7489 | 15699924.7647 | 15765342.2222 | 15831032.2524 | 15896995.9911 | 15963234.5788 | 16029749.1605 | 16096540.8863 | 16163610.911 | 16230960.3941 | 16298590.5 | 16992959.7169 | 16038599.3555 | 16105427.9627 | 16172535.0223 | 16239921.6948 | 16307589.145 | 16375538.5429 | 16443771.0634 | 16512287.886 | 16581090.1953 | 16650179.181 | 16719556.0374 | 16874436.636 | 16944747.904 | 17015352.1357 | 17086250.5516 | 17157444.3776 | 17228934.8446 | 17300723.1885 | 17372810.6505 | 17445198.4769 | 17517887.9193 | 17590880.2343 | 17664176.684 | 17823419.3478 | 17897684.7161 | 17972259.5233 | 18047145.059 | 18122342.6177 | 18197853.4996 | 18273679.0101 | 18349820.4603 | 18426279.1665 | 18503056.4506 | 18580153.6401 | 18657572.0679 | 18821382.1561 | 18899805.7083 | 18978556.0253 | 19057634.4686 | 19137042.4055 | 19216781.2087 | 19296852.257 | 19377256.9346 | 19457996.6318 | 19539072.7443 | 19620486.674 | 19702239.8283 | 19870833.1174 | 19953629.3876 | 20036770.6422 | 20120258.3188 | 20204093.8606 | 20288278.7173 | 20372814.3441 | 20457702.2027 | 20542943.7608 | 20628540.492 | 20714493.8762 | 20800805.3996 | 20974408.6163 | 21061803.1234 | 21149561.7742 | 21237686.0861 | 21326177.5827 | 21415037.7938 | 21504268.2558 | 21593870.5114 | 21683846.1097 | 21774196.6064 | 21864923.5634 | 21956028.5495
Accumulated Cash Flow | [13 empty] | 408427932.5533 | 405755365.8867 | 133046799.22 | 130634232.5533 | 128145536.6551 | 122852717.3568 | 114634898.0586 | 108562102.1604 | 101153565.9845 | 97297197.8944 | 93325749.3626 | 88574300.8309 | 84335902.2705 | 81119843.7161 | 73406651.5845 | 70681571.1522 | 70424421.9325 | 70166201.2577 | 69939144.6634 | 68544521.8109 | 61814088.0298 | 61607610.7746 | 75520298.6941 | 89913752.0449 | 104451127.0933 | 119049074.5377 | 134141180.0964 | 149296169.4283 | 164514304.5491 | 119995848.5662 | 135091899.0168 | 150250849.6775 | 165472962.6327 | 180758502.1573 | 196107732.5287 | 211520919.1256 | 227090822.1742 | 242725600.9231 | 258425525.6878 | 274190867.91 | 290021900.1625 | 305918896.1536 | 321882130.7324 | 337911879.8928 | 354008420.7791 | 370172031.6901 | 386402992.0841 | 402701582.5842 | 419694542.301 | 435733141.6565 | 451838569.6192 | 468011104.6415 | 484251026.3363 | 500558615.4813 | 516934154.0242 | 533377925.0875 | 549890212.9735 | 566471303.1688 | 583121482.3498 | 599841038.3872 | 616715475.0231 | 633660222.9272 | 650675575.0628 | 667761825.6144 | 684919269.9921 | 702148204.8367 | 719448928.0252 | 736821738.6756 | 754266937.1526 | 771784825.0719 | 789375705.3062 | 807039881.9902 | 824863301.3381 | 842760986.0541 | 860733245.5775 | 878780390.6365 | 896902733.2542 | 915100586.7537 | 933374265.7638 | 951724086.2241 | 970150365.3906 | 988653421.8412 | 1007233575.4813 | 1025891147.5493 | 1044712529.7053 | 1063612335.4136 | 1082590891.4389 | 1101648525.9075 | 1120785568.313 | 1140002349.5218 | 1159299201.7788 | 1178676458.7134 | 1198134455.3452 | 1217673528.0895 | 1237294014.7634 | 1256996254.5918 | 1276867087.7092 | 1296820717.0968 | 1316857487.739 | 1336977746.0578 | 1357181839.9184 | 1377470118.6357 | 1397842932.9798 | 1418300635.1826 | 1438843578.9433 | 1459472119.4353 | 1480186613.3116 | 1500987418.7112 | 1521961827.3274 | 1543023630.4508 | 1564173192.225 | 1585410878.3111 | 1606737055.8938 | 1628152093.6876 | 1649656361.9434 | 1671250232.4548 | 1692934078.5646 | 1714708275.1709 | 1736573198.7344 | 1758529227.2838
INDICATORS
| Own African palm oil production - Gal/Month | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460000 | 5460002 | 5460004 | 5460006 | 5460008 | 5460010 | 5460012 | 5460014 | 5460016 | 5460018 | 5460020 | 5460022 | 5460024 | 5460026 | 5460028 | 5460030 | 5460032 | 5460034 | 5460036 | 5460038 | 5460040 | 5460042 | 5460044 | 5460046 | 5460048 | 5460050 | 5460052 | 5460054 | 5460056 | 5460058 | 5460060 | 5460062 | 5460064 | 5460066 | 5460068 | 5460070 | 5460072 | 5460074 | 5460076 | 5460078 | 5460080 | 5460082 | 5460084 | 5460086 | 5460088 | 5460090 | 5460092 | 5460094 | 5460096 | 5460098 | 5460100 | 5460102 | 5460104 | 5460106 | 5460108 | 5460110 | 5460112 | 5460114 | 5460116 | 5460118 | 5460120 | 5460122 | 5460124 | 5460126 | 5460128 | 5460130 | 5460132 | 5460134 | 5460136 | 5460138 | 5460140 | 5460142 | 5460144 | 5460146 | 5460148 | 5460150 | 5460152 | 5460154 | 5460156 | 5460158 | 5460160 | 5460162 | 5460164 | 5460166 | 5460168 | 5460170 | 5460172 | 5460174
| Average sale price of Palm oil per gallon | [12 empty] | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734
| Average production cost of Palm oil per gallon | [12 empty] | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.0989 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1044 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1099 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.1155 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.121 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1266 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1323 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1379 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1436 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494 | 1.1494
| Gallons processed per month | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800 | 1801800.66 | 1801801.32 | 1801801.98 | 1801802.64 | 1801803.3 | 1801803.96 | 1801804.62 | 1801805.28 | 1801805.94 | 1801806.6 | 1801807.26 | 1801807.92 | 1801808.58 | 1801809.24 | 1801809.9 | 1801810.56 | 1801811.22 | 1801811.88 | 1801812.54 | 1801813.2 | 1801813.86 | 1801814.52 | 1801815.18 | 1801815.84 | 1801816.5 | 1801817.16 | 1801817.82 | 1801818.48 | 1801819.14 | 1801819.8 | 1801820.46 | 1801821.12 | 1801821.78 | 1801822.44 | 1801823.1 | 1801823.76 | 1801824.42 | 1801825.08 | 1801825.74 | 1801826.4 | 1801827.06 | 1801827.72 | 1801828.38 | 1801829.04 | 1801829.7 | 1801830.36 | 1801831.02 | 1801831.68 | 1801832.34 | 1801833 | 1801833.66 | 1801834.32 | 1801834.98 | 1801835.64 | 1801836.3 | 1801836.96 | 1801837.62 | 1801838.28 | 1801838.94 | 1801839.6 | 1801840.26 | 1801840.92 | 1801841.58 | 1801842.24 | 1801842.9 | 1801843.56 | 1801844.22 | 1801844.88 | 1801845.54 | 1801846.2 | 1801846.86 | 1801847.52 | 1801848.18 | 1801848.84 | 1801849.5 | 1801850.16 | 1801850.82 | 1801851.48 | 1801852.14 | 1801852.8 | 1801853.46 | 1801854.12 | 1801854.78 | 1801855.44 | 1801856.1 | 1801856.76 | 1801857.42
| Percentage of oil vs. Fruit | [12 empty] | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
| Hectares of Algae | [34 empty] | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
| Oil Production Gal/Month | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000 | 18750000
| Nafta Production Gal/Month | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000 | 6250000
| Green diesel price per Gallon | [12 empty] | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.2967 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3132 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3298 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3464 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3631 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3799 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.3968 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4138 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4309 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481 | 3.4481
| Average production cost of Biodiesel per Gallon | [12 empty] | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.7473 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.761 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8026 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8166 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8449 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8591 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734 | 2.8734
| Nafta price per Gallon | [12 empty] | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8315 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8407 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8499 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8591 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8684 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8777 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8871 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.8966 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9061 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156 | 1.9156
| Average production cost of Nafta per Gallon | [12 empty] | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2821 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2885 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.2949 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3014 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3079 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.3144 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.321 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3276 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3342 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409 | 1.3409
Costs & Sales Costs
| Annual price increase |  |  |  | 0.5%
| Discount rate |  |  |  | 12%
| Effective days per month |  |  |  | 20
| Annual Green diesel production |  |  |  | 15000 Gal
| Gallons per Metric Tons |  |  |  | 273
| Price of Green diesels per Metric Ton |  |  |  | 900
| Price of Nafta per Metric Ton |  |  |  | 500
| Price of African Palm Oil per Metric Ton |  |  |  | 750
| Production cost of Palm oil per metric ton |  |  |  | 300
| Production cost of Nafta per metric ton |  |  |  | 350
| Production cost of Green diesel per metric ton |  |  |  | 750
Note on P70: Fernando Andrade: days effective by month
Note on P78: Fernando Andrade: price by ton metric equal a 900. 1 tm = 273 gal

## financial gantt summary
FINANCIAL GANTT SUMMARY IBP CORP
| IBP CORP., FINANCIAL GANTT |  | initials |  | Beginning | duration Days | duration optimists | duration Supposed Duration | duration pessimist | pessimist used | optimistic USD | fin | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6 | YEAR 7 | YEAR 8 | YEAR 9 | YEAR 10
FUNDS USES
|  | Financial expenses, commissions and owed retainers | AG, AD, EF, JS, JCH | 7150000 | 39923 | 57 | 55 | 57 | 60 |  |  | 39934.7361 | 7150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paid out Capital | JXS, JS, AD, CP, JCH | 4550000 | 39923 | [6 empty] | 39934.7361 | 4550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auditing, Accounting, Legal & Miscellaneous | JXS, JS, AD | 2054000 | 39923 | [6 empty] | 39934.7361 | 2054000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unforeseen expenses | RB, PB, VM, DB, AD, JCH | 2600000 | 39923 | [6 empty] | 39934.7361 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labor and Salaries for the first 4 years & IBP payroll bank trust Account | AG, SC, DCM, MTP, SP, JCH | 26000000 | 39923 | [6 empty] | 39934.7361 | 6500000 | 6500000 | 6500000 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Office Quito and Panama and Italia | AD, JCH, JXS, HE, GE | 2340000 | 39923 | [6 empty] | 39934.7361 | 2340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Security & Surveillance Systems | AD, JCH, JXS, HE, GE | 689000 | 39923 | [6 empty] | 39934.7361 | 689000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Corporate, Fire, Flood, & Liability Insurance, Performance Bond | HE, PB, VM, SC | 585000 | 39923 | [6 empty] | 39934.7361 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency plan in Bank IBP Trust Account | EF, JS, AD, AG, JCH | 7150000 | 39923 | [6 empty] | 39934.7361 | 7150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Furniture, Fixtures, & Equipment | HE, VM, SC, JXS, MTP | 260000 | 39923 | [6 empty] | 39948.6806 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of 3080 (+/-) hectares for Industrial installations for African palm fruit process and extraction and refining oil and installation cost. | GE, HE, VM, PB | 10000000 | 39923 | [6 empty] | 39934.7361 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of 42 thousand (+/-) hectares to build Pools for the growing of Sea Algae, extraction plant for oil and Green Diesel refinery | AG, HE, VM, PB, JCH, EF, CP | 11303500 | 39923 | [6 empty] | 39934.7361 | 11303500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All Permits, | AG, HE, GE, AD, JCH, EF, DCM, CP | 1950000 | 39923 | [6 empty] | 39934.7361 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Property maintenance - cleaning of jungle weeds, wild vegetation, shrubbery | HE, AM, GE, VM, PB, RB, DC, JXS | 604500 | 39923 | [6 empty] | 40060.7361 | 604500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Micro Turbines 1.5 Kw/H | AG, HE, CP, AD, JS, AM, EF, DCM | 6110000 | 39984 | [6 empty] | 40490.6806 | 4888000 | 1222000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vegetable Oil production plant for Sea Algae with 3 expellers o produce a minimum of 15 thousand Gallons oil per Hct /Day | AG, HE, GE, DC, CP, AD, EF, JXS | 32760000 | 39984 | [6 empty] | 40518.6806 | 26208000 | 6552000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bio Diesel production plant conversion equipment and refinery & NAFTA Refinery | HE, GE, JXS, DC, SC, VM, JCH | 299000000 | 39984 | [6 empty] | 40791.6806 | 239200000 | 0 | 59800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Septic Tanks for 40 Hectares with leach lines included and construction of pools on of 15 Thousand Hectares for growing Sea Algae | HE, GE, JXS, DC, SC, JCH, CP | 1300000 | 40045 | [6 empty] | 40598.4306 | 547368.4211 | 752631.5789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical Recuperation Pools | GE, HE, AG, DC, JXS, JCH | 146455.4 | 40045 | [6 empty] | 40235.7361 | 61665.4316 | 84789.9684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of African Palm Fruit | JS, AD, HE, JXS, JCH | 5850046.8 | 40045 | [6 empty] | 40107.4861 | 5850046.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of African Palm 500.000 plants | PC, AD, EF, AM, PB, MT | 3250000 | 40076 | [6 empty] | 40130.7917 | 3250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase Sea Algae seed | AD, JS, JXS, HE | 2600000 | 40076 | [6 empty] | 40130.7917 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10Harvesting Boats for Sea Algae and harvesting & recollection docks for Sea Algae. | PC, HE, GE, AD, JXS | 1560000 | 40106 | [6 empty] | 40641.4861 | 1560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stationary Irrigation System and water drain channels | PC, HE, EF, MT | 1950000 | 40137 | [6 empty] | 40653.4861 | 1560000 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Septic Tanks for 40 Acres with leach lines Santa Elena | JCH, AD, HE, PB, MT | 322400 | 40137 | [6 empty] | 40437.7917 | 128960 | 193440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ocean Cargo Boat Loading Dock and floating peer | PC, HE, EF, DC | 5200000 | 40137 | [6 empty] | 40611.4861 | 1386666.6667 | 3813333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vehicles, harvesting equipment such as Haul Tractors, Harvest Baskets, Construction of Harvest Gathering and Warehousing, (8 tractors, 10 trucks) | RB, DCM, JS, AG | 3566453.8 | 40137 | [6 empty] | 40158.7917 | 3566453.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 Land movement Tractors & 1 Rear excavator equipment And two bulldozers with rear excavators | MTP, MT, PC, DC, VM | 1300000 | 40137 | [6 empty] | 40311.7917 | 650000 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction of office site Infrastructure in San Lorenzo and Santa Elena | MT, MTP, VM, AG, HE, GE | 609177.92 | 40137 | [6 empty] | 40479.7917 | 221519.2436 | 387658.6764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Housing for employees Santa Elena / San Lorenzo | MTP, VM, MT, DC, AM, DCM | 2600000 | 40167 | [6 empty] | 40942.7917 | 600000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Septic Tanks for 10 hectares with leach lines included and pools San Lorenzo | AD, AG, JS, EF, RB, DCM, JCH | 1300000 | 40167 | [6 empty] | 40386.6806 | 557142.8571 | 742857.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | School, Medical center, Food Distribution Center and Church (Santa Elena $2.000.000 and San Lorenzo $1.000.000) | AD,. AG, JS, HE, GE, EF | 1950000 | 40167 | [6 empty] | 40735.7361 | 835714.2857 | 1114285.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power and Phone Line installation | AD, AG, JCH, RB, JXS | 1380965.3 | 40198 | [6 empty] | 40582.4306 | 230160.8833 | 1150804.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electricity & Fuel for 2 Years | AD, JCH, AG, JXS, JS | 195000 | 40257 | [6 empty] | 41278.7917 | 0 | 97500 | 97500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Storage tanks in Ecuador at property for the Vegetable Oil and Bio Diesel and Storage Tanks at Port site for Bio Diesel to be exported. extracted oil and bio Diesel | AG, AD, JCH, JS, EF, DC | 5200000 | 40318 | [6 empty] | 40680.4861 | 0 | 4333333.3333 | 866666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Associated Research & Development with USA and European Universities |  | 4030000 | 40318 | [6 empty] | 40401.7917 | 0 | 4030000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sea Water Tax |  | 45500 | 40318 | [6 empty] | 40331.7361 | 0 | 45500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Oil production cost | [10 empty] | 0 | 19899000 | 23998198.3953 | 24118268.8977 | 24238966.7863 | 24360268.697 | 24482177.6527 | 24604696.6912 | 24727828.8656 | 24851577.2444
|  | Bi Product production (Nafta / and others) | [10 empty] | 0 | 16105769.2308 | 97117788.4615 | 97603377.4038 | 98091394.2909 | 98581851.2623 | 99074760.5186 | 99570134.3212 | 100067984.9928 | 100568324.9178
|  | green diesel production cost | [10 empty] | 0 | 103537087.9121 | 624328640.1099 | 627450283.3104 | 630587534.727 | 633740472.4006 | 636909174.7626 | 640093720.6364 | 643294189.2396 | 646510660.1858
|  | Financial costs | [10 empty] | 19250000 | 21000000 | 21000000 | 21000000 | 32276820.17 | 33301985.64 | 33301985.64 | 33301985.64 | 33301985.64 | 33301985.64
| Operative uses | [11 empty] | 370887698.3891 | 194601991.3071 | 833708793.6334 | 776671929.612 | 785194715.9742 | 789984578 | 793768098.574 | 797570537.2889 | 801391988.7381 | 805232547.988
| Total uses |  |  | 459461999.22 | [8 empty] | 370887698.3891 | 194601991.3071 | 833708793.6334 | 776671929.612 | 785194715.9742 | 789984578 | 793768098.574 | 797570537.2889 | 801391988.7381 | 805232547.988
459461999.22
|  | Total Needed Funds |  | 459461999.22
FUNDS SOURCES
|  | Credit | [10 empty] | 459461999.22
|  | Sale of African palm oil | [10 empty] | 0 | 44772750 | 59995495.9882 | 60295672.2444 | 60597416.9658 | 60900671.7426 | 61205444.1317 | 61511741.728 | 61819572.1641 | 62128943.111
|  | Sale of Biodiesel | [10 empty] | 0 | 124244505.4945 | 749194368.1319 | 752940339.9725 | 756705041.6724 | 760488566.8808 | 764291009.7152 | 768112464.7637 | 771953027.0875 | 775812792.223
|  | Sale of Nafta and other bi products | [10 empty] | 0 | 23008241.7582 | 138739697.8022 | 139433396.2912 | 140130563.2727 | 140831216.089 | 141535372.1695 | 142243049.0303 | 142954264.2755 | 143669035.5968
|  | Sale of Electricity to main Grid at $ 0,04 Cents Kw/H |  | 265384.6154 | [8 empty] | 0 | 265384.6154 | 265384.6154 | 265384.6154 | 265384.6154 | 265384.6154 | 265384.6154 | 265384.6154 | 265384.6154 | 265384.6154
|  | Sale of CDF´s | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financial income | [10 empty] | 0 |  |  | 14917799.9471 | 24635765.2509 | 34697582.2753 | 45322153.5013 | 56543004.1939 | 68390904.715 | 80898201.0145
| Operative sources | [11 empty] | 0 | 192290881.8681 | 948194946.5376 | 967852593.0706 | 982334171.7771 | 997183421.6031 | 1012619364.133 | 1028675644.3313 | 1045383152.8575 | 1062774356.5607
| Total Sources | [11 empty] | 0 | 192290881.8681 | 948194946.5376 | 967852593.0706 | 982334171.7771 | 997183421.6031 | 1012619364.133 | 1028675644.3313 | 1045383152.8575 | 1062774356.5607
| Annual net cash flow | [11 empty] | -370887698.3891 | -2311109.4389 | 114486152.9043 | 191180663.4586 | 197139455.803 | 207198843.6031 | 218851265.5591 | 231105107.0425 | 243991164.1194 | 257541808.5727
| ACUMULATED CASH FLOW | [11 empty] | 88574300.8309 | 86263191.3919 | 200749344.2962 | 391930007.7548 | 589069463.5578 | 796268307.1609 | 1015119572.7199 | 1246224679.7624 | 1490215843.8818 | 1747757652.4545
Senario 1 |  | (TIR) INTERNAL RATE OF RETURN AT 12% ANAUAL INTERSET (NET ANNUAL CASH FLOW) |  | 31.38% | [9 empty] | EVALUADORES DEL PROYECTO
|  | (VAN) NET ACTUAL VALUE AT 12% WILL REPRESENT |  | 3179953769.63
[14 empty] | FIRST EVALUATOR |  | SECOND EVALUATOR
Senario 2 |  | (TIR) INTERNAL RATE OF RETURN AT 10% ANAUAL INTERSET (NET ANNUAL CASH FLOW) |  | 33.14% | [9 empty] | VAN= -INVERSION + ∑ FC / (a+i)^n |  | 33.14%
|  | (VAN) NET ACTUAL VALUE AT 10% WILL REPRESENT |  | 3340124596.8265 | [9 empty] | 3340124596.8265
Senario 3 |  | (TIR) INTERNAL RATE OF RETURN AT 9% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE 32% |  | 32.86%
|  | (VAN) NET ACTUAL VALUE AT 9% WILL REPRESENT € 2.439.464.515,50 |  | 3305726414.03 | [9 empty] | THRE EVALUATOR
BENEFICIO VS COSTO
Senario 4 |  | (TIR) INTERNAL RATE OF RETURN AT 8% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 33% |  | 33.37% | [9 empty] | bc= sumatoria de ingresos deflactados/sumatoria de egresos deflactados
|  | (VAN) NET ACTUAL VALUE AT 8% INTEST WILL REPRESENT € 2.537.936.657,73 |  | 3347650628.83 | [9 empty] | bc=∑id | 4098577271.9377 | 1.1234
[14 empty] | ∑ed | 3648502146.459
Srenario 5 |  | (TIR) INTERNAL RATE OF RETURN AT 7% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 33% |  | 33.88% | [20 empty] | Elaborado por: | Jorge Sagal Pazmiño
|  | (VAN) NET ACTUAL VALUE AT 7% INTEST WILL REPRESENT € 2.582.408.799,95 |  | 3389574843.63 | [9 empty] | FOUR EVALUATOR
Tasa de rendimiento beneficio costo
Senario 6 |  | (TIR) INTERNAL RATE OF RETURN AT 6% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 34% |  | 34.4% | [9 empty] | trbc=∑id | 4098577271.9377 | 8.9204
|  | (VAN) NET ACTUAL VALUE AT 6% INTEST WILL REPRESENT € 2.626.880.942,18 |  | 3431499058.43 | [9 empty] | inversion | 459461999.22
Senario 7 |  | (TIR) INTERNAL RATE OF RETURN AT 5% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 35% |  | 34.93% | [9 empty] | FIVE EVALUATOR
|  | (VAN) NET ACTUAL VALUE AT 5% INTEST WILL REPRESENT € 2.671.353.084,40 |  | 3473423273.23 | [9 empty] | Retorno de la Inversion (recuperacion de la inversion)
Senario 8 | [13 empty] | Ingresos
|  | (TIR) INTERNAL RATE OF RETURN AT 4% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 36% |  | 35.46% | [9 empty] | Ingresos Corrientes |  | Ingresos Deflactados
|  | (VAN) NET ACTUAL VALUE AT4% INTEST WILL REPRESENT € 2.715.825.226,63 |  | 3515347488.03 | [9 empty] | 1140485828.4058 |  | 828199547.7561
[14 empty] | 459461999.22 |  | 459461999.22
[14 empty] | 1.6115 |  | 2.2191
SIX EVALUATOR
Valor real.
[14 empty] | 981492661.4903 | 2.1362
459461999.22
Evaluación del proyecto IBP CORP
[14 empty] | Primer evaluador del proyecto |  |  | Analisis
[14 empty] | Valor de Rescate, VAN. |  |  | El proyecto me devuelve EUR 557'777.773,90 más, con el dinero de hoy, esto no es tan cierto si esque los escenarios no cambian
Calculo: VAN= -inversion + la sumatoria de flujos de caja FC/(a+i) esponenciado a la n
VAN= -INVERSION + ∑ FC / (a+i)^n
[14 empty] | 459461999.22 | 459461999.22 | 0
Segundo Evaluador del proyecto
TIR= Tasa de retorno (no es la rentabilidad) cuanto me devuelve el proyecto cuando esta funcionando.
Calculo de la tasa interna de retorno
[14 empty] | Inversion | año 1 | año 2 | año 3 | año 4 | año 5 | año 6 | año 7 | año 8 | año 9 | año 10
[14 empty] | -459461999.22 | -370887698.3891 | -2311109.4389 | 114486152.9043 | 191180663.4586 | 197139455.803 | 207198843.6031 | 218851265.5591 | 231105107.0425 | 243991164.1194 | 257541808.5727
[14 empty] | TIR= | año 1: 33.14%; año 2: El retorno se hace con una velocidad del 26,11%, este proyecto se asemeja a la realidad. Un proyecto bien estructurado no debe devolver mas del 30%, En la practica el TIR no debe sobrepasar mas de 10 puntos sobre la tasa de rendimiento neto, esto quiere decir, deberia de devolverme el 30 (20,56+10) hasta el 30.
[14 empty] | VAN= | año 1: -6.4355e-08; año 3: -6.4355e-08; año 4: El van vale cero, esto quiere decir que se encontro la tasa interna de retorno es lo que me devuelve el 24,50% anual
Tercer Evaluador del proyecto
[14 empty] | Factor de concesión o valor de oportunidad del credito. | año 2: Analizar con cuanto contribuye el credito a la toma de decision incial.
Fator de concesion= fa=credito inicial- la sumatoria de las obligaciones financieras deflactadas
[14 empty] | TRM | año 5: BANCO
[14 empty] | Gastos Financieros | TRM | TRMn | Total |  | Gtos Financieros | i Bancario | in | Total
[14 empty] | 19250000 | 1.12 | 1.12 | 17187500 |  | 19250000 | 1.1123 | 1.1123 | 17306482.0642
[14 empty] | 21000000 | 1.12 | 1.2544 | 16741071.4286 |  | 21000000 | 1.1123 | 1.2372 | 16973656.941
[14 empty] | 21000000 | 1.12 | 1.4049 | 14947385.2041 |  | 21000000 | 1.1123 | 1.3762 | 15259963.0864
[14 empty] | 21000000 | 1.12 | 1.5735 | 13345879.6465 |  | 21000000 | 1.1123 | 1.5307 | 13719287.1405
[14 empty] | 32276820.17 | 1.12 | 1.7623 | 18314734.5817 |  | 32276820.17 | 1.1123 | 1.7026 | 18957499.6423
[14 empty] | 33301985.64 | 1.12 | 1.9738 | 16871822.3222 |  | 33301985.64 | 1.1123 | 1.8938 | 17584843.4312
[14 empty] | 33301985.64 | 1.12 | 2.2107 | 15064127.0734 |  | 33301985.64 | 1.1123 | 2.1065 | 15809442.9841
[14 empty] | 33301985.64 | 1.12 | 2.476 | 13450113.4584 |  | 33301985.64 | 1.1123 | 2.343 | 14213290.4649
[14 empty] | 33301985.64 | 1.12 | 2.7731 | 12009029.8736 |  | 33301985.64 | 1.1123 | 2.6061 | 12778288.6495
[14 empty] | 33301985.64 | 1.12 | 3.1058 | 10722348.1014 |  | 33301985.64 | 1.1123 | 2.8988 | 11488167.4454
[14 empty] | Total | año 3: 62221836.2792; año 5: Total; año 8: 63259389.2321
[14 empty] | Fa=inversion-sumatoria de obligaciones | año 5: Fa=inversion-sumatoria de obligaciones
[14 empty] | Fa= | año 1: 397240162.9408; año 2: Es la erocion del dinero en los 10 años, afectados por la inflación.; año 5: Fa=; año 6: 396202609.9879
[14 empty] | Si sale positivo el prestamo si me benficio, y si sale negativo el prestamo no me ayudo, estoy recibiendo 290'778.163,72 euros mas de lo que voy a pagar a futuro, por la deflactacion. | año 6: Esta perdiendo el banco siempre cuando no reajuste tasas, pero el banco reajusta cada 3 meses
Cuarto evaluador del proyecto
Beneficio costo (Cuanto recibo y cuanto gasto)
bc= sumatoria de ingresos deflactados/sumatoria de egresos deflactados
[14 empty] | bc=∑id | año 1: 4098577271.9377; año 2: 1.1234; año 3: Analisis
[14 empty] | ∑ed | año 1: 3648502146.459; año 3: Por cada dólar gastado recibo 1,08 dolares de ingresos
Ingresos
[14 empty] | Año1 | Año2 | Año3 | Año4 | Año5 | Año6 | Año7 | Año8 | Año9 | Año10
[14 empty] | 0 | 192290881.8681 | 948194946.5376 | 967852593.0706 | 982334171.7771 | 997183421.6031 | 1012619364.133 | 1028675644.3313 | 1045383152.8575 | 1062774356.5607
[14 empty] | 1.12 | 1.2544 | 1.4049 | 1.5735 | 1.7623 | 1.9738 | 2.2107 | 2.476 | 2.7731 | 3.1058
[14 empty] | 0 | 153293113.7342 | 674906434.022 | 615087820.1274 | 557402790.3564 | 505204154.9062 | 458057574.8005 | 415464839.7763 | 376975644.8673 | 342184899.3474
Egresos
[14 empty] | Año1 | Año2 | Año3 | Año4 | Año5 | Año6 | Año7 | Año8 | Año9 | Año10
[14 empty] | 370887698.3891 | 194601991.3071 | 833708793.6334 | 776671929.612 | 785194715.9742 | 789984578 | 793768098.574 | 797570537.2889 | 801391988.7381 | 805232547.988
[14 empty] | 1.12 | 1.2544 | 1.4049 | 1.5735 | 1.7623 | 1.9738 | 2.2107 | 2.476 | 2.7731 | 3.1058
[14 empty] | 331149730.7046 | 155135516.0292 | 593417451.7366 | 493589052.258 | 445540568.8121 | 400230772.4649 | 359060376.5494 | 322125363.1415 | 288989985.0789 | 259263329.6839
Quinto evaluador del proyecto
[14 empty] | Tasa de rendimiento beneficio costo |  |  | Analisis
[14 empty] | Es igual a sumatoria de ingresos deflactados/para la inversion inicial. |  |  | Cada dólar invertido produce 11,55 euros de ingresos, los ingresos son 11,55 veces mas que la inversion, Sobre la inversion voy a tener realmente 11,55
[14 empty] | trbc=∑id | 4098577271.9377 | 8.9204
[14 empty] | inversion | 459461999.22
Sexto evaluador del proyecto
Retorno de la Inversion (recuperacion de la inversion)
Tiempo de recuperacion es igual, ( se aplica la regla de tres simple)
Ingresos
[14 empty] | Año1 | Año2 | Año3 | Año4 | Año5
[14 empty] | 0 | 192290881.8681 | 948194946.5376 | 967852593.0706 | 982334171.7771 | 997183421.6031 | 1012619364.133 | 1028675644.3313 | 1045383152.8575 | 1062774356.5607
[14 empty] | 1.12 | 1.2544 | 1.4049 | 1.5735 | 1.7623 | 1.9738 | 2.2107 | 2.476 | 2.7731 | 3.1058
[14 empty] | 0 | 153293113.7342 | 674906434.022 | 615087820.1274 | 557402790.3564 | 505204154.9062 | 458057574.8005 | 415464839.7763 | 376975644.8673 | 342184899.3474
Ingresos Corrientes
1140485828.4058
[14 empty] | 459461999.22 | corresponde a x
[14 empty] | 1.6115 | Analisis | Esto quiere decir que en aproximademente al 2 año empiezo a recuperarla inversion
Ingresos Deflactados
[14 empty] | 828199547.7561 | corresponde a un año
[14 empty] | 459461999.22 | corresponde a x
[14 empty] | 2.2191 | Analisis | Esto quiere decir que en aproximademente al 2 año empiezo a recuperarla inversion
Septimo evaluador del proyecto
Valor real.
[14 empty] | 828199547.7561 | 153293113.7342
[14 empty] | 981492661.4903 | 2.1362 | Analisis | A los tres años recupero la inversion.
459461999.22
[14 empty] | Egresos Año10: Elaborado por: | Jorge Sagal Pazmiño
Note on O212: jsagal: sumo los dos años porque no me alcanza con el un año

## Financial Gantt Summary detalla
FINANCIAL GANT SUMMARY IBP CORP
| IBP CORP., FINANCIAL GANTT |  | initials |  | Beginning | duration Days | duration optimists | duration Supposed Duration | duration pessimist | pessimist used | optimistic USD | fin | YEAR 1 | AVERAGE OF MONTH of the FIRST YEAR | AVERAGE OF FIRST WEAKS OF FIRST YEAR | AVERAGE OF FIRST DAY OF FIRST YEAR | AVERAGE OF HOUR FIRST YEAR | AVERAGE OF First MINUTE OF HOUR FIRST YEAR | YEAR 2 | AVERAGE OF MONTHS SECOND YEAR | AVERAGE OF WEAKS SECOND YEAR | AVERAGE OF DAY SECOND YEAR | AVERAGE OF HOUR`S SECOND YEAR | AVERAGE OF MINUTE OF HOUR SECOND YEAR | YEAR 3 | AVERAGE OF MONTH`S THREE YEAR | AVERAGE OF WEAKS THREE YEAR | AVERAGE OF DAY THREE YEAR | AVERAGE OF HOUR`S THREE YEAR | AVERAGE OF MINUTE OF HOUR THREE YEAR | YEAR 4 | AVERAGE OF MONTH`S FOUR YEAR | AVERAGE OF WEAKS FOUR YEAR | AVERAGE OF DAY FOUR YEAR | AVERAGE OF HOUR`S FOUR YEAR | AVERAGE OF MINUTE OF HOUR FOUR YEAR | YEAR 5 | AVERAGE OF MONTH`S FIVE YEAR | AVERAGE OF WEAKS FIVE YEAR | AVERAGE OF DAY FIVE YEAR | AVERAGE OF HOUR`S FIVE YEAR | AVERAGE OF MINUTE OF FIVE FOUR YEAR | YEAR 6 | AVERAGE OF MONTH`S SIXE YEAR | AVERAGE OF WEAKS SIXE YEAR | AVERAGE OF DAY SIX YEAR | AVERAGE OF HOUR`S SIXE YEAR | AVERAGE OF MINUTE OF SIXE HOUR YEAR | YEAR 7 | AVERAGE OF MONTH`S SEVEN YEAR | AVERAGE OF WEAKS SEVEN YEAR | AVERAGE OF DAY SEVEN YEAR | AVERAGE OF HOUR`S SEVEN YEAR | AVERAGE OF MINUTE OF HOUR SEVEN YEAR | YEAR 8 | AVERAGE OF MONTH`S EIGHT YEAR | AVERAGE OF WEAKS EIGTH YEAR | AVERAGE OF DAY EIGHT YEAR | AVERAGE OF HOUR`S EIGTH YEAR | AVERAGE OF MINUTE OF HOUR EIGHT YEAR | YEAR 9 | AVERAGE OF MONTH`S NINE YEAR | AVERAGE OF WEAKS NINE YEAR | AVERAGE OF DAY NINE YEAR | AVERAGE OF HOUR`S NINE YEAR | AVERAGE OF MINUTE OF HOUR NINE YEAR | YEAR 10 | AVERAGE OF MONTH`S TEN YEAR | AVERAGE OF WEAKS TEN YEAR | AVERAGE OF DAY NINE YEAR | AVERAGE OF HOUR`S TEN YEAR | AVERAGE OF MINUTE OF HOUR TEN YEAR
FUNDS USES
|  | Financial expenses, commissions and owed retainers | AG, AD, EF, JS, JCH | 7150000 | 39923 | 57 | 55 | 57 | 60 |  |  | 39934.7361 | 7150000 | 595833.3333 | 148958.3333 | 21279.7619 | 816.21 | 13.6035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paid out Capital | JXS, JS, AD, CP, JCH | 4550000 | 39923 | [6 empty] | 39934.7361 | 4550000 | 379166.6667 | 94791.6667 | 13541.6667 | 519.4064 | 8.6568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auditing, Accounting, Legal & Miscellaneous | JXS, JS, AD | 2054000 | 39923 | [6 empty] | 39934.7361 | 2054000 | 171166.6667 | 42791.6667 | 6113.0952 | 234.4749 | 3.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unforeseen expenses | RB, PB, VM, DB, AD, JCH | 2600000 | 39923 | [6 empty] | 39934.7361 | 2600000 | 216666.6667 | 54166.6667 | 7738.0952 | 296.8037 | 4.9467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labor and Salaries for the first 4 years & IBP payroll bank trust Account | AG, SC, DCM, MTP, SP, JCH | 26000000 | 39923 | [6 empty] | 39934.7361 | 6500000 | 541666.6667 | 135416.6667 | 19345.2381 | 742.0091 | 12.3668 | 6500000 | 541666.6667 | 135416.6667 | 19345.2381 | 742.0091 | 12.3668 | 6500000 | 541666.6667 | 135416.6667 | 19345.2381 | 742.0091 | 12.3668 | 6500000 | 541666.6667 | 135416.6667 | 19345.2381 | 742.0091 | 12.3668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Office Quito and Panama and Italia | AD, JCH, JXS, HE, GE | 2340000 | 39923 | [6 empty] | 39934.7361 | 2340000 | 195000 | 48750 | 6964.2857 | 267.1233 | 4.4521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Security & Surveillance Systems | AD, JCH, JXS, HE, GE | 689000 | 39923 | [6 empty] | 39934.7361 | 689000 | 57416.6667 | 14354.1667 | 2050.5952 | 78.653 | 1.3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Corporate, Fire, Flood, & Liability Insurance, Performance Bond | HE, PB, VM, SC | 585000 | 39923 | [6 empty] | 39934.7361 | 585000 | 48750 | 12187.5 | 1741.0714 | 66.7808 | 1.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency plan in Bank IBP Trust Account | EF, JS, AD, AG, JCH | 7150000 | 39923 | [6 empty] | 39934.7361 | 7150000 | 595833.3333 | 148958.3333 | 21279.7619 | 816.21 | 13.6035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Furniture, Fixtures, & Equipment | HE, VM, SC, JXS, MTP | 260000 | 39923 | [6 empty] | 39948.6806 | 260000 | 21666.6667 | 5416.6667 | 773.8095 | 29.6804 | 0.49467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of 3080 (+/-) hectares for Industrial installations for African palm fruit process and extraction and refining oil and installation cost. | GE, HE, VM, PB | 10000000 | 39923 | [6 empty] | 39934.7361 | 10000000 | 833333.3333 | 208333.3333 | 29761.9048 | 1141.5525 | 19.0259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of 42 thousand (+/-) hectares to build Pools for the growing of Sea Algae, extraction plant for oil and Green Diesel refinery | AG, HE, VM, PB, JCH, EF, CP | 11303500 | 39923 | [6 empty] | 39934.7361 | 11303500 | 941958.3333 | 235489.5833 | 33641.369 | 1290.3539 | 21.5059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All Permits, | AG, HE, GE, AD, JCH, EF, DCM, CP | 1950000 | 39923 | [6 empty] | 39934.7361 | 1950000 | 162500 | 40625 | 5803.5714 | 222.6027 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Property maintenance - cleaning of jungle weeds, wild vegetation, shrubbery | HE, AM, GE, VM, PB, RB, DC, JXS | 604500 | 39923 | [6 empty] | 40060.7361 | 604500 | 50375 | 12593.75 | 1799.1071 | 69.0068 | 1.1501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Micro Turbines 1.5 Kw/H | AG, HE, CP, AD, JS, AM, EF, DCM | 6110000 | 39984 | [6 empty] | 40490.6806 | 4888000 | 407333.3333 | 101833.3333 | 14547.619 | 557.9909 | 9.2998 | 1222000 | 101833.3333 | 25458.3333 | 3636.9048 | 139.4977 | 2.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vegetable Oil production plant for Sea Algae with 3 expellers o produce a minimum of 15 thousand Gallons oil per Hct /Day | AG, HE, GE, DC, CP, AD, EF, JXS | 32760000 | 39984 | [6 empty] | 40518.6806 | 26208000 | 2184000 | 546000 | 78000 | 2991.7808 | 49.863 | 6552000 | 546000 | 136500 | 19500 | 747.9452 | 12.4658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bio Diesel production plant conversion equipment and refinery & NAFTA Refinery | HE, GE, JXS, DC, SC, VM, JCH | 299000000 | 39984 | [6 empty] | 40791.6806 | 239200000 | 19933333.3333 | 4983333.3333 | 711904.7619 | 27305.9361 | 455.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 59800000 | 4983333.3333 | 1245833.3333 | 177976.1905 | 6826.484 | 113.7747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Septic Tanks for 40 Hectares with leach lines included and construction of pools on of 15 Thousand Hectares for growing Sea Algae | HE, GE, JXS, DC, SC, JCH, CP | 1300000 | 40045 | [6 empty] | 40598.4306 | 547368.4211 | 45614.0351 | 11403.5088 | 1629.0727 | 62.485 | 1.0414 | 752631.5789 | 62719.2982 | 15679.8246 | 2239.9749 | 85.9168 | 1.4319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical Recuperation Pools | GE, HE, AG, DC, JXS, JCH | 146455.4 | 40045 | [6 empty] | 40235.7361 | 61665.4316 | 5138.786 | 1284.6965 | 183.5281 | 7.0394 | 0.11732 | 84789.9684 | 7065.8307 | 1766.4577 | 252.3511 | 9.6792 | 0.16132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of African Palm Fruit | JS, AD, HE, JXS, JCH | 5850046.8 | 40045 | [6 empty] | 40107.4861 | 5850046.8 | 487503.9 | 121875.975 | 17410.8536 | 667.8136 | 11.1302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase of African Palm 500.000 plants | PC, AD, EF, AM, PB, MT | 3250000 | 40076 | [6 empty] | 40130.7917 | 3250000 | 270833.3333 | 67708.3333 | 9672.619 | 371.0046 | 6.1834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Purchase Sea Algae seed | AD, JS, JXS, HE | 2600000 | 40076 | [6 empty] | 40130.7917 | 2600000 | 216666.6667 | 54166.6667 | 7738.0952 | 296.8037 | 4.9467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10Harvesting Boats for Sea Algae and harvesting & recollection docks for Sea Algae. | PC, HE, GE, AD, JXS | 1560000 | 40106 | [6 empty] | 40641.4861 | 1560000 | 130000 | 32500 | 4642.8571 | 178.0822 | 2.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stationary Irrigation System and water drain channels | PC, HE, EF, MT | 1950000 | 40137 | [6 empty] | 40653.4861 | 1560000 | 130000 | 32500 | 4642.8571 | 178.0822 | 2.968 | 390000 | 32500 | 8125 | 1160.7143 | 44.5205 | 0.74201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Septic Tanks for 40 Acres with leach lines Santa Elena | JCH, AD, HE, PB, MT | 322400 | 40137 | [6 empty] | 40437.7917 | 128960 | 10746.6667 | 2686.6667 | 383.8095 | 14.7215 | 0.24536 | 193440 | 16120 | 4030 | 575.7143 | 22.0822 | 0.36804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ocean Cargo Boat Loading Dock and floating peer | PC, HE, EF, DC | 5200000 | 40137 | [6 empty] | 40611.4861 | 1386666.6667 | 115555.5556 | 28888.8889 | 4126.9841 | 158.2953 | 2.6383 | 3813333.3333 | 317777.7778 | 79444.4444 | 11349.2063 | 435.312 | 7.2552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vehicles, harvesting equipment such as Haul Tractors, Harvest Baskets, Construction of Harvest Gathering and Warehousing, (8 tractors, 10 trucks) | RB, DCM, JS, AG | 3566453.8 | 40137 | [6 empty] | 40158.7917 | 3566453.8 | 297204.4833 | 74301.1208 | 10614.4458 | 407.1294 | 6.7855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 Land movement Tractors & 1 Rear excavator equipment And two bulldozers with rear excavators | MTP, MT, PC, DC, VM | 1300000 | 40137 | [6 empty] | 40311.7917 | 650000 | 54166.6667 | 13541.6667 | 1934.5238 | 74.2009 | 1.2367 | 650000 | 54166.6667 | 13541.6667 | 1934.5238 | 74.2009 | 1.2367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction of office site Infrastructure in San Lorenzo and Santa Elena | MT, MTP, VM, AG, HE, GE | 609177.92 | 40137 | [6 empty] | 40479.7917 | 221519.2436 | 18459.937 | 4614.9842 | 659.2835 | 25.2876 | 0.42146 | 387658.6764 | 32304.8897 | 8076.2224 | 1153.7461 | 44.2533 | 0.73755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Housing for employees Santa Elena / San Lorenzo | MTP, VM, MT, DC, AM, DCM | 2600000 | 40167 | [6 empty] | 40942.7917 | 600000 | 50000 | 12500 | 1785.7143 | 68.4932 | 1.1416 | 2000000 | 166666.6667 | 41666.6667 | 5952.381 | 228.3105 | 3.8052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Septic Tanks for 10 hectares with leach lines included and pools San Lorenzo | AD, AG, JS, EF, RB, DCM, JCH | 1300000 | 40167 | [6 empty] | 40386.6806 | 557142.8571 | 46428.5714 | 11607.1429 | 1658.1633 | 63.6008 | 1.06 | 742857.1429 | 61904.7619 | 15476.1905 | 2210.8844 | 84.801 | 1.4134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | School, Medical center, Food Distribution Center and Church (Santa Elena $2.000.000 and San Lorenzo $1.000.000) | AD,. AG, JS, HE, GE, EF | 1950000 | 40167 | [6 empty] | 40735.7361 | 835714.2857 | 69642.8571 | 17410.7143 | 2487.2449 | 95.4012 | 1.59 | 1114285.7143 | 92857.1429 | 23214.2857 | 3316.3265 | 127.2016 | 2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power and Phone Line installation | AD, AG, JCH, RB, JXS | 1380965.3 | 40198 | [6 empty] | 40582.4306 | 230160.8833 | 19180.0736 | 4795.0184 | 685.0026 | 26.2741 | 0.4379 | 1150804.4167 | 95900.3681 | 23975.092 | 3425.0131 | 131.3704 | 2.1895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electricity & Fuel for 2 Years | AD, JCH, AG, JXS, JS | 195000 | 40257 | [6 empty] | 41278.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 97500 | 8125 | 2031.25 | 290.1786 | 11.1301 | 0.1855 | 97500 | 8125 | 2031.25 | 290.1786 | 11.1301 | 0.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Storage tanks in Ecuador at property for the Vegetable Oil and Bio Diesel and Storage Tanks at Port site for Bio Diesel to be exported. extracted oil and bio Diesel | AG, AD, JCH, JS, EF, DC | 5200000 | 40318 | [6 empty] | 40680.4861 | 0 | 0 | 0 | 0 | 0 | 0 | 4333333.3333 | 361111.1111 | 90277.7778 | 12896.8254 | 494.6728 | 8.2445 | 866666.6667 | 72222.2222 | 18055.5556 | 2579.3651 | 98.9346 | 1.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Associated Research & Development with USA and European Universities |  | 4030000 | 40318 | [6 empty] | 40401.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 4030000 | 335833.3333 | 83958.3333 | 11994.0476 | 460.0457 | 7.6674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sea Water Tax |  | 45500 | 40318 | [6 empty] | 40331.7361 | 0 | 0 | 0 | 0 | 0 | 0 | 45500 | 3791.6667 | 947.9167 | 135.4167 | 5.1941 | 0.086568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Oil production cost | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 19899000 | 1658250 | 414562.5 | 59223.2143 | 2271.5753 | 37.8596 | 23998198.3953 | 1999849.8663 | 499962.4666 | 71423.2095 | 2739.5204 | 45.6587 | 24118268.8977 | 2009855.7415 | 502463.9354 | 71780.5622 | 2753.227 | 45.8871 | 24238966.7863 | 2019913.8989 | 504978.4747 | 72139.7821 | 2767.0053 | 46.1168 | 24360268.697 | 2030022.3914 | 507505.5979 | 72500.7997 | 2780.8526 | 46.3475 | 24482177.6527 | 2040181.4711 | 510045.3678 | 72863.624 | 2794.7691 | 46.5795 | 24604696.6912 | 2050391.3909 | 512597.8477 | 73228.264 | 234.0629 | 3.901 | 24727828.8656 | 2060652.4055 | 515163.1014 | 73594.7288 | 2822.8115 | 47.0469 | 24851577.2444 | 2070964.7704 | 517741.1926 | 73963.0275 | 2836.938 | 47.2823
|  | Bi Product production (Nafta / and others) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16105769.2308 | 1342147.4359 | 335536.859 | 47933.837 | 1838.5581 | 30.6426 | 97117788.4615 | 8093149.0385 | 2023287.2596 | 289041.0371 | 11086.5055 | 184.7751 | 97603377.4038 | 8133614.7837 | 2033403.6959 | 290486.2423 | 11141.9381 | 185.699 | 98091394.2909 | 8174282.8576 | 2043570.7144 | 291938.6735 | 11197.6478 | 186.6275 | 98581851.2623 | 8215154.2719 | 2053788.568 | 293398.3669 | 11253.636 | 187.5606 | 99074760.5186 | 8256230.0432 | 2064057.5108 | 294865.3587 | 11309.9042 | 188.4984 | 99570134.3212 | 8297511.1934 | 2074377.7984 | 296339.6855 | 947.2045 | 15.7867 | 100067984.9928 | 8338998.7494 | 2084749.6874 | 297821.3839 | 11423.286 | 190.3881 | 100568324.9178 | 8380693.7431 | 2095173.4358 | 299310.4908 | 11480.4024 | 191.34
|  | green diesel production cost | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 103537087.9121 | 8628090.6593 | 2157022.6648 | 308146.095 | 11819.3023 | 196.9884 | 624328640.1099 | 52027386.6758 | 13006846.669 | 1858120.9527 | 71270.3927 | 1187.8399 | 627450283.3104 | 52287523.6092 | 13071880.9023 | 1867411.5575 | 71626.7447 | 1193.7791 | 630587534.727 | 52548961.2272 | 13137240.3068 | 1876748.6153 | 71984.8784 | 1199.748 | 633740472.4006 | 52811706.0334 | 13202926.5083 | 1886132.3583 | 72344.8028 | 1205.7467 | 636909174.7626 | 53075764.5636 | 13268941.1409 | 1895563.0201 | 72706.5268 | 1211.7754 | 640093720.6364 | 53341143.3864 | 13335285.8466 | 1905040.8352 | 6089.1716 | 101.4862 | 643294189.2396 | 53607849.1033 | 13401962.2758 | 1914566.0394 | 73435.4097 | 1223.9235 | 646510660.1858 | 53875888.3488 | 13468972.0872 | 1924138.8696 | 73802.5868 | 1230.0431
|  | Financial costs | [10 empty] | 19250000 | 1604166.6667 | 401041.6667 | 57291.6667 | 2197.4886 | 36.6248 | 21000000 | 1750000 | 437500 | 62500 | 2397.2603 | 39.9543 | 21000000 | 1750000 | 437500 | 62500 | 2397.2603 | 39.9543 | 21000000 | 1750000 | 437500 | 62500 | 2397.2603 | 39.9543 | 32276820.17 | 2689735.0142 | 672433.7535 | 96061.9648 | 3684.5685 | 61.4095 | 33301985.64 | 2775165.47 | 693791.3675 | 99113.0525 | 3801.5965 | 63.3599 | 33301985.64 | 2775165.47 | 693791.3675 | 99113.0525 | 3801.5965 | 63.3599 | 33301985.64 | 2775165.47 | 693791.3675 | 99113.0525 | 316.7997 | 5.28 | 33301985.64 | 2775165.47 | 693791.3675 | 99113.0525 | 3801.5965 | 63.3599 | 33301985.64 | 2775165.47 | 693791.3675 | 99113.0525 | 3801.5965 | 63.3599
[14 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Operative uses | [11 empty] | 370887698.3891 | 30907308.1991 | 7726827.0498 | 1103832.4357 | 42338.7784 | 705.6463 | 194601991.3071 | 16216832.6089 | 4054208.1522 | 579172.5932 | 22214.8392 | 370.2473 | 833708793.6334 | 69475732.8028 | 17368933.2007 | 2481276.1715 | 95172.2367 | 1586.2039 | 776671929.612 | 64722660.801 | 16180665.2003 | 2311523.6 | 88661.1792 | 1477.6863 | 785194715.9742 | 65432892.9978 | 16358223.2495 | 2336889.0356 | 89634.1 | 1493.9017 | 789984578 | 65832048.1667 | 16458012.0417 | 2351144.5774 | 90180.8879 | 1503.0148 | 793768098.574 | 66147341.5478 | 16536835.387 | 2362405.0553 | 90612.7966 | 1510.2133 | 797570537.2889 | 66464211.4407 | 16616052.8602 | 2373721.8372 | 7587.2387 | 126.454 | 801391988.7381 | 66782665.7282 | 16695666.432 | 2385095.2046 | 91483.1037 | 1524.7184 | 805232547.988 | 67102712.3323 | 16775678.0831 | 2396525.4404 | 91921.5237 | 1532.0254
| Total uses |  |  | 459461999.22 | [8 empty] | 370887698.3891 | 30907308.1991 | 7726827.0498 | 1103832.4357 | 42338.7784 | 705.6463 | 194601991.3071 | 16216832.6089 | 4054208.1522 | 579172.5932 | 22214.8392 | 370.2473 | 833708793.6334 | 69475732.8028 | 17368933.2007 | 2481276.1715 | 95172.2367 | 1586.2039 | 776671929.612 | 64722660.801 | 16180665.2003 | 2311523.6 | 88661.1792 | 1477.6863 | 785194715.9742 | 65432892.9978 | 16358223.2495 | 2336889.0356 | 89634.1 | 1493.9017 | 789984578 | 65832048.1667 | 16458012.0417 | 2351144.5774 | 90180.8879 | 1503.0148 | 793768098.574 | 66147341.5478 | 16536835.387 | 2362405.0553 | 90612.7966 |  | 797570537.2889 | 66464211.4407 | 16616052.8602 | 2373721.8372 | 7587.2387 | 126.454 | 801391988.7381 | 66782665.7282 | 16695666.432 | 2385095.2046 | 91483.1037 | 1524.7184 | 805232547.988 | 67102712.3323 | 16775678.0831 | 2396525.4404 | 91921.5237 | 1532.0254
459461999.22
|  | Total Needed Funds |  | 459461999.22
FUNDS SOURCES
|  | Credit | [10 empty] | 459461999.22 | 38288499.935 | 9572124.9838 | 1367446.4263 | 52449.9999 | 874.1667 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
|  | Sale of African palm oil | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 44772750 | 3731062.5 | 932765.625 | 133252.2321 | 5111.0445 | 85.1841 | 59995495.9882 | 4999624.6657 | 1249906.1664 | 178558.0238 | 6848.8009 | 114.1467 | 60295672.2444 | 5024639.3537 | 1256159.8384 | 179451.4055 | 6883.0676 | 114.7178 | 60597416.9658 | 5049784.7471 | 1262446.1868 | 180349.4553 | 6917.5134 | 115.2919 | 60900671.7426 | 5075055.9785 | 1268763.9946 | 181251.9992 | 6952.1315 | 115.8689 | 61205444.1317 | 5100453.6776 | 1275113.4194 | 182159.0599 | 6986.9228 | 116.4487 | 61511741.728 | 5125978.4773 | 1281494.6193 | 183070.6599 | 585.1574 | 9.7526 | 61819572.1641 | 5151631.0137 | 1287907.7534 | 183986.8219 | 7057.0288 | 117.6171 | 62128943.111 | 5177411.9259 | 1294352.9815 | 184907.5688 | 7092.3451 | 118.2058
|  | Sale of Biodiesel | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 124244505.4945 | 10353708.7912 | 2588427.1978 | 369775.314 | 14183.1627 | 236.386 | 749194368.1319 | 62432864.011 | 15608216.0027 | 2229745.1432 | 85524.4712 | 1425.4079 | 752940339.9725 | 62745028.331 | 15686257.0828 | 2240893.869 | 85952.0936 | 1432.5349 | 756705041.6724 | 63058753.4727 | 15764688.3682 | 2252098.3383 | 86381.8541 | 1439.6976 | 760488566.8808 | 63374047.2401 | 15843511.81 | 2263358.83 | 86813.7633 | 1446.8961 | 764291009.7152 | 63690917.4763 | 15922729.3691 | 2274675.6242 | 87247.8322 | 1454.1305 | 768112464.7637 | 64009372.0636 | 16002343.0159 | 2286049.0023 | 7307.0059 | 121.7834 | 771953027.0875 | 64329418.924 | 16082354.731 | 2297479.2473 | 88122.4917 | 1468.7082 | 775812792.223 | 64651066.0186 | 16162766.5046 | 2308966.6435 | 88563.1041 | 1476.0517
|  | Sale of Nafta and other bi products | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 23008241.7582 | 1917353.4799 | 479338.37 | 68476.91 | 2626.5116 | 43.7752 | 138739697.8022 | 11561641.4835 | 2890410.3709 | 412915.7673 | 15837.865 | 263.9644 | 139433396.2912 | 11619449.6909 | 2904862.4227 | 414980.3461 | 15917.0544 | 265.2842 | 140130563.2727 | 11677546.9394 | 2919386.7348 | 417055.2478 | 15996.6396 | 266.6107 | 140831216.089 | 11735934.6741 | 2933983.6685 | 419140.5241 | 16076.6228 | 267.9437 | 141535372.1695 | 11794614.3475 | 2948653.5869 | 421236.2267 | 16157.006 | 269.2834 | 142243049.0303 | 11853587.4192 | 2963396.8548 | 423342.4078 | 1353.1492 | 22.5525 | 142954264.2755 | 11912855.3563 | 2978213.8391 | 425459.1199 | 16318.9799 | 271.983 | 143669035.5968 | 11972419.6331 | 2993104.9083 | 427586.4155 | 16400.5748 | 273.3429
|  | Sale of Electricity to main Grid at $ 0,04 Cents Kw/H | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 2.5246 | 0.042076 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492 | 265384.6154 | 22115.3846 | 5528.8462 | 789.8352 | 30.295 | 0.50492
|  | Sale of CDF´s | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Financial income | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3650560.653 | 304213.3877 | 76053.3469 | 10864.7638 | 416.7307 | 6.9455 | 7121014.1764 | 593417.848 | 148354.462 | 21193.4946 | 812.9012 | 13.5484 | 14917799.9471 | 1243149.9956 | 310787.4989 | 44398.2141 | 1702.9452 | 28.3824 | 24635765.2509 | 2052980.4376 | 513245.1094 | 73320.7299 | 2812.302 | 46.8717 | 34697582.2753 | 2891465.1896 | 722866.2974 | 103266.6139 | 3960.9112 | 66.0152 | 45322153.5013 | 3776846.1251 | 944211.5313 | 134887.3616 | 5173.7618 | 86.2294 | 56543004.1939 | 4711917.0162 | 1177979.254 | 168282.7506 | 537.8901 | 8.9648 | 68390904.715 | 5699242.0596 | 1424810.5149 | 203544.3593 | 7807.1809 | 130.1197 | 80898201.0145 | 6741516.7512 | 1685379.1878 | 240768.4554 | 9234.9545 | 153.9159
[14 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Operative sources | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 195941442.5211 | 16328453.5434 | 4082113.3859 | 583159.0551 | 22367.7446 | 372.7957 | 955315960.714 | 79609663.3928 | 19902415.8482 | 2843202.264 | 109054.3334 | 1817.5722 | 967852593.0706 | 80654382.7559 | 20163595.689 | 2880513.6699 | 110485.4558 | 1841.4243 | 982334171.7771 | 81861180.9814 | 20465295.2454 | 2923613.6065 | 112138.6041 | 1868.9767 | 997183421.6031 | 83098618.4669 | 20774654.6167 | 2967807.8024 | 113833.7239 | 1897.2287 | 1012619364.133 | 84384947.0111 | 21096236.7528 | 3013748.1075 | 115595.8178 | 1926.597 | 1028675644.3313 | 85722970.3609 | 21430742.5902 | 3061534.6557 | 9785.7272 | 163.0955 | 1045383152.8575 | 87115262.7381 | 21778815.6845 | 3111259.3835 | 119335.9764 | 1988.9329 | 1062774356.5607 | 88564529.7134 | 22141132.4283 | 3163018.9183 | 121321.2736 | 2022.0212
| Total Sources | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 195941442.5211 | 16328453.5434 | 4082113.3859 | 583159.0551 | 22367.7446 | 372.7957 | 955315960.714 | 79609663.3928 | 19902415.8482 | 2843202.264 | 109054.3334 | 1817.5722 | 967852593.0706 | 80654382.7559 | 20163595.689 | 2880513.6699 | 110485.4558 | 1841.4243 | 982334171.7771 | 81861180.9814 | 20465295.2454 | 2923613.6065 | 112138.6041 | 1868.9767 | 997183421.6031 | 83098618.4669 | 20774654.6167 | 2967807.8024 | 113833.7239 | 1897.2287 | 1012619364.133 | 84384947.0111 | 21096236.7528 | 3013748.1075 | 115595.8178 |  | 1028675644.3313 | 85722970.3609 | 21430742.5902 | 3061534.6557 | 9785.7272 | 163.0955 | 1045383152.8575 | 87115262.7381 | 21778815.6845 | 3111259.3835 | 119335.9764 | 1988.9329 | 1062774356.5607 | 88564529.7134 | 22141132.4283 | 3163018.9183 | 121321.2736 | 2022.0212
| Annual net cash flow | [11 empty] | -370887698.3891 | [5 empty] | 1339451.2141 | [5 empty] | 121607167.0806 | [5 empty] | 191180663.4586 | [5 empty] | 197139455.803 | [5 empty] | 207198843.6031 | [5 empty] | 218851265.5591 | [5 empty] | 231105107.0425 | [5 empty] | 243991164.1194 | [5 empty] | 257541808.5727
| ACUMULATED CASH FLOW | [11 empty] | 88574300.8309 | [5 empty] | 89913752.0449 | [5 empty] | 211520919.1256 | [5 empty] | 402701582.5842 | [5 empty] | 599841038.3872 | [5 empty] | 807039881.9902 | [5 empty] | 1025891147.5493 | [5 empty] | 1256996254.5918 | [5 empty] | 1500987418.7112 | [5 empty] | 1758529227.2838
[71 empty] | Elaborado por: | Jorge Sagal Pazmiño
SENARIO OF PROYECT
Senario 1 |  | (TIR) INTERNAL RATE OF RETURN AT 12% ANAUAL INTERSET (NET ANNUAL CASH FLOW) |  | 0.3138 | [9 empty] | EVALUADORES DEL PROYECTO
|  | (VAN) NET ACTUAL VALUE AT 12% WILL REPRESENT |  | 3179953769.63
[14 empty] | FIRST EVALUATOR |  | SECOND EVALUATOR
Senario 2 |  | (TIR) INTERNAL RATE OF RETURN AT 10% ANAUAL INTERSET (NET ANNUAL CASH FLOW) |  | 0.33139 | [9 empty] | VAN= -INVERSION + ∑ FC / (a+i)^n |  | 33.14%
|  | (VAN) NET ACTUAL VALUE AT 10% WILL REPRESENT |  | 3340124596.8265 | [9 empty] | 3340124596.8265
Senario 3 |  | (TIR) INTERNAL RATE OF RETURN AT 9% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE 32% |  | 0.3286
|  | (VAN) NET ACTUAL VALUE AT 9% WILL REPRESENT € 2.439.464.515,50 |  | 3305726414.03 | [9 empty] | THRE EVALUATOR
BENEFICIO VS COSTO
Senario 4 |  | (TIR) INTERNAL RATE OF RETURN AT 8% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 33% |  | 0.3337
|  | (VAN) NET ACTUAL VALUE AT 8% INTEST WILL REPRESENT € 2.537.936.657,73 |  | 3347650628.83 | [9 empty] | bc=∑id | 4098577271.9377 | 1.1234
[14 empty] | ∑ed | 3648502146.459
Srenario 5 |  | (TIR) INTERNAL RATE OF RETURN AT 7% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 33% |  | 0.3388
|  | (VAN) NET ACTUAL VALUE AT 7% INTEST WILL REPRESENT € 2.582.408.799,95 |  | 3389574843.63 | [9 empty] | FOUR EVALUATOR
Senario 6 |  | (TIR) INTERNAL RATE OF RETURN AT 6% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 34% |  | 0.344 | [9 empty] | trbc=∑id | 4098577271.9377 | 8.9204
|  | (VAN) NET ACTUAL VALUE AT 6% INTEST WILL REPRESENT € 2.626.880.942,18 |  | 3431499058.43 | [9 empty] | inversion | 459461999.22
Senario 7 |  | (TIR) INTERNAL RATE OF RETURN AT 5% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 35% |  | 0.3493 | [9 empty] | FIVE EVALUATOR
|  | (VAN) NET ACTUAL VALUE AT 5% INTEST WILL REPRESENT € 2.671.353.084,40 |  | 3473423273.23 | [9 empty] | Retorno de la Inversion (recuperacion de la inversion)
Ingresos
Senario 8 |  | (TIR) INTERNAL RATE OF RETURN AT 4% ANNUAL INTEREST (NET ANNUAL CASH FLOW) WILL BE AT 36% |  | 0.3546 | [9 empty] | Ingresos Corrientes |  | Ingresos Deflactados
|  | (VAN) NET ACTUAL VALUE AT4% INTEST WILL REPRESENT € 2.715.825.226,63 |  | 3515347488.03 | [9 empty] | 1140485828.4058 |  | 828199547.7561
[14 empty] | 459461999.22 |  | 459461999.22
[14 empty] | 1.6115 |  | 2.2191
SIX EVALUATOR
Valor real.
[14 empty] | 981492661.4903 | 2.1362
459461999.22
Evaluación del proyecto IBP CORP
[14 empty] | Primer evaluador del proyecto |  |  | Analisis
[14 empty] | Valor de Rescate, VAN. |  |  | El proyecto me devuelve EUR 557'777.773,90 más, con el dinero de hoy, esto no es tan cierto si esque los escenarios no cambian
Calculo: VAN= -inversion + la sumatoria de flujos de caja FC/(a+i) esponenciado a la n
VAN= -INVERSION + ∑ FC / (a+i)^n
[14 empty] | 459461999.22 | 459461999.22 | 0
Segundo Evaluador del proyecto
TIR= Tasa de retorno (no es la rentabilidad) cuanto me devuelve el proyecto cuando esta funcionando.
Calculo de la tasa interna de retorno
[14 empty] | Inversion | año 1 | año 2 | año 3 | año 4 | año 5 | año 6 | año 7 | año 8 | año 11 | año 12
[14 empty] | -459461999.22 | -370887698.3891 | 1339451.2141 | 121607167.0806 | 191180663.4586 | 197139455.803 | 207198843.6031 | 218851265.5591 | 231105107.0425 | 243991164.1194 | 257541808.5727
[14 empty] | TIR= | año 1: 33.67%; año 2: El retorno se hace con una velocidad del 26,11%, este proyecto se asemeja a la realidad. Un proyecto bien estructurado no debe devolver mas del 30%, En la practica el TIR no debe sobrepasar mas de 10 puntos sobre la tasa de rendimiento neto, esto quiere decir, deberia de devolverme el 30 (20,56+10) hasta el 30.
[14 empty] | VAN= | año 1: 6.4098e-08; año 3: 6.4098e-08; año 4: El van vale cero, esto quiere decir que se encontro la tasa interna de retorno es lo que me devuelve el 24,50% anual
Tercer Evaluador del proyecto
[14 empty] | Factor de concesión o valor de oportunidad del credito. | año 2: Analizar con cuanto contribuye el credito a la toma de decision incial.
Fator de concesion= fa=credito inicial- la sumatoria de las obligaciones financieras deflactadas
[14 empty] | TRM | año 5: BANCO
[14 empty] | Gastos Financieros | TRM | TRMn | Total |  | Gtos Financieros | i Bancario | in | Total
[14 empty] | 19250000 | 1.12 | 1.12 | 17187500 |  | 19250000 | 1.1123 | 1.1123 | 17306482.0642
[14 empty] | 21000000 | 1.12 | 1.2544 | 16741071.4286 |  | 21000000 | 1.1123 | 1.2372 | 16973656.941
[14 empty] | 21000000 | 1.12 | 1.4049 | 14947385.2041 |  | 21000000 | 1.1123 | 1.3762 | 15259963.0864
[14 empty] | 21000000 | 1.12 | 1.5735 | 13345879.6465 |  | 21000000 | 1.1123 | 1.5307 | 13719287.1405
[14 empty] | 32276820.17 | 1.12 | 1.7623 | 18314734.5817 |  | 32276820.17 | 1.1123 | 1.7026 | 18957499.6423
[14 empty] | 33301985.64 | 1.12 | 1.9738 | 16871822.3222 |  | 33301985.64 | 1.1123 | 1.8938 | 17584843.4312
[14 empty] | 33301985.64 | 1.12 | 2.2107 | 15064127.0734 |  | 33301985.64 | 1.1123 | 2.1065 | 15809442.9841
[14 empty] | 33301985.64 | 1.12 | 2.476 | 13450113.4584 |  | 33301985.64 | 1.1123 | 2.343 | 14213290.4649
[14 empty] | 33301985.64 | 1.12 | 2.7731 | 12009029.8736 |  | 33301985.64 | 1.1123 | 2.6061 | 12778288.6495
[14 empty] | 33301985.64 | 1.12 | 3.1058 | 10722348.1014 |  | 33301985.64 | 1.1123 | 2.8988 | 11488167.4454
[14 empty] | Total | año 3: 62221836.2792; año 5: Total; año 8: 63259389.2321
[14 empty] | Fa=inversion-sumatoria de obligaciones | año 5: Fa=inversion-sumatoria de obligaciones
[14 empty] | Fa= | año 1: 397240162.9408; año 2: Es la erocion del dinero en los 10 años, afectados por la inflación.; año 5: Fa=; año 6: 396202609.9879
[14 empty] | Si sale positivo el prestamo si me benficio, y si sale negativo el prestamo no me ayudo, estoy recibiendo 290'778.163,72 euros mas de lo que voy a pagar a futuro, por la deflactacion. | año 6: Esta perdiendo el banco siempre cuando no reajuste tasas, pero el banco reajusta cada 3 meses
Cuarto evaluador del proyecto
Beneficio costo (Cuanto recibo y cuanto gasto)
bc= sumatoria de ingresos deflactados/sumatoria de egresos deflactados
[14 empty] | bc=∑id | año 1: 4106556073.775; año 2: 1.1255; año 3: Analisis
[14 empty] | ∑ed | año 1: 3648502146.459; año 3: Por cada dólar gastado recibo 1,08 dolares de ingresos
Ingresos
[14 empty] | Año1 | Año2 | Año3 | Año4 | Año5 | Año6 | Año7 | Año8 | Año9 | Año10
[14 empty] | 0 | 195941442.5211 | 955315960.714 | 967852593.0706 | 982334171.7771 | 997183421.6031 | 1012619364.133 | 1028675644.3313 | 1045383152.8575 | 1062774356.5607
[14 empty] | 1.12 | 1.2544 | 1.4049 | 1.5735 | 1.7623 | 1.9738 | 2.2107 | 2.476 | 2.7731 | 3.1058
[14 empty] | 0 | 156203318.3364 | 679975031.2571 | 615087820.1274 | 557402790.3564 | 505204154.9062 | 458057574.8005 | 415464839.7763 | 376975644.8673 | 342184899.3474
Egresos
[14 empty] | Año1 | Año2 | Año3 | Año4 | Año5 | Año6 | Año7 | Año8 | Año9 | Año10
[14 empty] | 370887698.3891 | 194601991.3071 | 833708793.6334 | 776671929.612 | 785194715.9742 | 789984578 | 793768098.574 | 797570537.2889 | 801391988.7381 | 805232547.988
[14 empty] | 1.12 | 1.2544 | 1.4049 | 1.5735 | 1.7623 | 1.9738 | 2.2107 | 2.476 | 2.7731 | 3.1058
[14 empty] | 331149730.7046 | 155135516.0292 | 593417451.7366 | 493589052.258 | 445540568.8121 | 400230772.4649 | 359060376.5494 | 322125363.1415 | 288989985.0789 | 259263329.6839
Quinto evaluador del proyecto
[14 empty] | Tasa de rendimiento beneficio costo |  |  | Analisis
[14 empty] | Es igual a sumatoria de ingresos deflactados/para la inversion inicial. |  |  | Cada dólar invertido produce 11,55 euros de ingresos, los ingresos son 11,55 veces mas que la inversion, Sobre la inversion voy a tener realmente 11,55
[14 empty] | trbc=∑id | 4106556073.775 | 8.9377
[14 empty] | inversion | 459461999.22
Sexto evaluador del proyecto
Retorno de la Inversion (recuperacion de la inversion)
Tiempo de recuperacion es igual, ( se aplica la regla de tres simple)
Ingresos
[14 empty] | Año1 | Año2 | Año3 | Año4 | Año5
[14 empty] | 0 | 195941442.5211 | 955315960.714 | 967852593.0706 | 982334171.7771 | 997183421.6031 | 1012619364.133 | 1028675644.3313 | 1045383152.8575 | 1062774356.5607
[14 empty] | 1.12 | 1.2544 | 1.4049 | 1.5735 | 1.7623 | 1.9738 | 2.2107 | 2.476 | 2.7731 | 3.1058
[14 empty] | 0 | 156203318.3364 | 679975031.2571 | 615087820.1274 | 557402790.3564 | 505204154.9062 | 458057574.8005 | 415464839.7763 | 376975644.8673 | 342184899.3474
Ingresos Corrientes
1151257403.2351
[14 empty] | 459461999.22 | corresponde a x
[14 empty] | 1.5964 | Analisis | Esto quiere decir que en aproximademente al 2 año empiezo a recuperarla inversion
Ingresos Deflactados
[14 empty] | 836178349.5935 | corresponde a un año
[14 empty] | 459461999.22 | corresponde a x
[14 empty] | 2.1979 | Analisis | Esto quiere decir que en aproximademente al 2 año empiezo a recuperarla inversion
Septimo evaluador del proyecto
Valor real.
[14 empty] | 836178349.5935 | 156203318.3364
[14 empty] | 992381667.9298 | 2.1599 | Analisis | A los tres años recupero la inversion.
459461999.22
[14 empty] | Egresos Año10: Elaborado por: | Jorge Sagal Pazmiño
Note on O380: jsagal: sumo los dos años porque no me alcanza con el un año

## Amortization table
| Loan | 210000000 | VA |  | 30.4167
| Annual Rate | 10% | i |  | 0.0083333
| Annual payments | 12 | q |  | 120
| Grace Period (years) | 4 | j | f PAGO | -2775165.4745 | 2775165.47
| Period in years | 10 Starting after grace period | n |  | -2775165.4745
| First payment date | 2009-05-31
Payment | Date | Interest payment |  | Payment | Date | Initial Capital | Interests | C.Amortiz. | Pending capital
1 | 2015-12-30 | 1750000 |  | 1 | 2019-12-29 | 210000000 | 1750000 | -1025165.4745 | 208974834.5255
2 | 2016-01-29 10:00 | 1750000 |  | 2 | 2020-01-28 10:00 | 208974834.5255 | 1741456.9544 | -1033708.5201 | 207941126.0053
3 | 2016-02-28 20:00 | 1750000 |  | 3 | 2020-02-27 20:00 | 207941126.0053 | 1732842.7167 | -1042322.7578 | 206898803.2475
4 | 2016-03-30 06:00 | 1750000 |  | 4 | 2020-03-29 06:00 | 206898803.2475 | 1724156.6937 | -1051008.7808 | 205847794.4668
5 | 2016-04-29 16:00 | 1750000 |  | 5 | 2020-04-28 16:00 | 205847794.4668 | 1715398.2872 | -1059767.1873 | 204788027.2795
6 | 2016-05-30 02:00 | 1750000 |  | 6 | 2020-05-29 02:00 | 204788027.2795 | 1706566.894 | -1068598.5805 | 203719428.6989
7 | 2016-06-29 12:00 | 1750000 |  | 7 | 2020-06-28 12:00 | 203719428.6989 | 1697661.9058 | -1077503.5687 | 202641925.1302
8 | 2016-07-29 22:00 | 1750000 |  | 8 | 2020-07-28 22:00 | 202641925.1302 | 1688682.7094 | -1086482.7651 | 201555442.3651
9 | 2016-08-29 08:00 | 1750000 |  | 9 | 2020-08-28 08:00 | 201555442.3651 | 1679628.6864 | -1095536.7881 | 200459905.577
10 | 2016-09-28 18:00 | 1750000 |  | 10 | 2020-09-27 18:00 | 200459905.577 | 1670499.2131 | -1104666.2614 | 199355239.3156
11 | 2016-10-29 04:00 | 1750000 |  | 11 | 2020-10-28 04:00 | 199355239.3156 | 1661293.661 | -1113871.8136 | 198241367.5021
12 | 2016-11-28 14:00 | 1750000 |  | 12 | 2020-11-27 14:00 | 198241367.5021 | 1652011.3959 | -1123154.0787 | 197118213.4234
13 | 2016-12-29 | 1750000 |  | 13 | 2020-12-28 | 197118213.4234 | 1642651.7785 | -1132513.696 | 195985699.7274
14 | 2017-01-28 10:00 | 1750000 |  | 14 | 2021-01-27 10:00 | 195985699.7274 | 1633214.1644 | -1141951.3101 | 194843748.4173
15 | 2017-02-27 20:00 | 1750000 |  | 15 | 2021-02-26 20:00 | 194843748.4173 | 1623697.9035 | -1151467.571 | 193692280.8463
16 | 2017-03-30 06:00 | 1750000 |  | 16 | 2021-03-29 06:00 | 193692280.8463 | 1614102.3404 | -1161063.1341 | 192531217.7121
17 | 2017-04-29 16:00 | 1750000 |  | 17 | 2021-04-28 16:00 | 192531217.7121 | 1604426.8143 | -1170738.6602 | 191360479.0519
18 | 2017-05-30 02:00 | 1750000 |  | 18 | 2021-05-29 02:00 | 191360479.0519 | 1594670.6588 | -1180494.8158 | 190179984.2361
19 | 2017-06-29 12:00 | 1750000 |  | 19 | 2021-06-28 12:00 | 190179984.2361 | 1584833.202 | -1190332.2725 | 188989651.9636
20 | 2017-07-29 22:00 | 1750000 |  | 20 | 2021-07-28 22:00 | 188989651.9636 | 1574913.7664 | -1200251.7082 | 187789400.2554
21 | 2017-08-29 08:00 | 1750000 |  | 21 | 2021-08-28 08:00 | 187789400.2554 | 1564911.6688 | -1210253.8057 | 186579146.4497
22 | 2017-09-28 18:00 | 1750000 |  | 22 | 2021-09-27 18:00 | 186579146.4497 | 1554826.2204 | -1220339.2541 | 185358807.1956
23 | 2017-10-29 04:00 | 1750000 |  | 23 | 2021-10-28 04:00 | 185358807.1956 | 1544656.7266 | -1230508.7479 | 184128298.4477
24 | 2017-11-28 14:00 | 1750000 |  | 24 | 2021-11-27 14:00 | 184128298.4477 | 1534402.4871 | -1240762.9875 | 182887535.4603
25 | 2017-12-29 | 1750000 |  | 25 | 2021-12-28 | 182887535.4603 | 1524062.7955 | -1251102.679 | 181636432.7812
26 | 2018-01-28 10:00 | 1750000 |  | 26 | 2022-01-27 10:00 | 181636432.7812 | 1513636.9398 | -1261528.5347 | 180374904.2466
27 | 2018-02-27 20:00 | 1750000 |  | 27 | 2022-02-26 20:00 | 180374904.2466 | 1503124.2021 | -1272041.2725 | 179102862.9741
28 | 2018-03-30 06:00 | 1750000 |  | 28 | 2022-03-29 06:00 | 179102862.9741 | 1492523.8581 | -1282641.6164 | 177820221.3577
29 | 2018-04-29 16:00 | 1750000 |  | 29 | 2022-04-28 16:00 | 177820221.3577 | 1481835.178 | -1293330.2965 | 176526891.0612
30 | 2018-05-30 02:00 | 1750000 |  | 30 | 2022-05-29 02:00 | 176526891.0612 | 1471057.4255 | -1304108.049 | 175222783.0122
31 | 2018-06-29 12:00 | 1750000 |  | 31 | 2022-06-28 12:00 | 175222783.0122 | 1460189.8584 | -1314975.6161 | 173907807.3961
32 | 2018-07-29 22:00 | 1750000 |  | 32 | 2022-07-28 22:00 | 173907807.3961 | 1449231.7283 | -1325933.7462 | 172581873.6499
33 | 2018-08-29 08:00 | 1750000 |  | 33 | 2022-08-28 08:00 | 172581873.6499 | 1438182.2804 | -1336983.1941 | 171244890.4558
34 | 2018-09-28 18:00 | 1750000 |  | 34 | 2022-09-27 18:00 | 171244890.4558 | 1427040.7538 | -1348124.7207 | 169896765.735
35 | 2018-10-29 04:00 | 1750000 |  | 35 | 2022-10-28 04:00 | 169896765.735 | 1415806.3811 | -1359359.0934 | 168537406.6417
36 | 2018-11-28 14:00 | 1750000 |  | 36 | 2022-11-27 14:00 | 168537406.6417 | 1404478.3887 | -1370687.0858 | 167166719.5558
37 | 2018-12-29 | 1750000 |  | 37 | 2022-12-28 | 167166719.5558 | 1393055.9963 | -1382109.4782 | 165784610.0776
38 | 2019-01-28 10:00 | 1750000 |  | 38 | 2023-01-27 10:00 | 165784610.0776 | 1381538.4173 | -1393627.0572 | 164390983.0204
39 | 2019-02-27 20:00 | 1750000 |  | 39 | 2023-02-26 20:00 | 164390983.0204 | 1369924.8585 | -1405240.616 | 162985742.4044
40 | 2019-03-30 06:00 | 1750000 |  | 40 | 2023-03-29 06:00 | 162985742.4044 | 1358214.52 | -1416950.9545 | 161568791.4499
41 | 2019-04-29 16:00 | 1750000 |  | 41 | 2023-04-28 16:00 | 161568791.4499 | 1346406.5954 | -1428758.8791 | 160140032.5708
42 | 2019-05-30 02:00 | 1750000 |  | 42 | 2023-05-29 02:00 | 160140032.5708 | 1334500.2714 | -1440665.2031 | 158699367.3677
43 | 2019-06-29 12:00 | 1750000 |  | 43 | 2023-06-28 12:00 | 158699367.3677 | 1322494.7281 | -1452670.7465 | 157246696.6213
44 | 2019-07-29 22:00 | 1750000 |  | 44 | 2023-07-28 22:00 | 157246696.6213 | 1310389.1385 | -1464776.336 | 155781920.2852
45 | 2019-08-29 08:00 | 1750000 |  | 45 | 2023-08-28 08:00 | 155781920.2852 | 1298182.669 | -1476982.8055 | 154304937.4798
46 | 2019-09-28 18:00 | 1750000 |  | 46 | 2023-09-27 18:00 | 154304937.4798 | 1285874.479 | -1489290.9955 | 152815646.4843
47 | 2019-10-29 04:00 | 1750000 |  | 47 | 2023-10-28 04:00 | 152815646.4843 | 1273463.7207 | -1501701.7538 | 151313944.7304
48 | 2019-11-28 14:00 | 1750000 |  | 48 | 2023-11-27 14:00 | 151313944.7304 | 1260949.5394 | -1514215.9351 | 149799728.7953
|  |  |  | 49 | 2023-12-28 | 149799728.7953 | 1248331.0733 | -1526834.4012 | 148272894.3941
|  |  |  | 50 | 2024-01-27 10:00 | 148272894.3941 | 1235607.4533 | -1539558.0212 | 146733336.3729
|  |  |  | 51 | 2024-02-26 20:00 | 146733336.3729 | 1222777.8031 | -1552387.6714 | 145180948.7015
|  |  |  | 52 | 2024-03-28 06:00 | 145180948.7015 | 1209841.2392 | -1565324.2353 | 143615624.4661
|  |  |  | 53 | 2024-04-27 16:00 | 143615624.4661 | 1196796.8706 | -1578368.604 | 142037255.8622
|  |  |  | 54 | 2024-05-28 02:00 | 142037255.8622 | 1183643.7989 | -1591521.6757 | 140445734.1865
|  |  |  | 55 | 2024-06-27 12:00 | 140445734.1865 | 1170381.1182 | -1604784.3563 | 138840949.8302
|  |  |  | 56 | 2024-07-27 22:00 | 138840949.8302 | 1157007.9153 | -1618157.5593 | 137222792.271
|  |  |  | 57 | 2024-08-27 08:00 | 137222792.271 | 1143523.2689 | -1631642.2056 | 135591150.0654
|  |  |  | 58 | 2024-09-26 18:00 | 135591150.0654 | 1129926.2505 | -1645239.224 | 133945910.8414
|  |  |  | 59 | 2024-10-27 04:00 | 133945910.8414 | 1116215.9237 | -1658949.5508 | 132286961.2905
|  |  |  | 60 | 2024-11-26 14:00 | 132286961.2905 | 1102391.3441 | -1672774.1304 | 130614187.1601
|  |  |  | 61 | 2024-12-27 | 130614187.1601 | 1088451.5597 | -1686713.9148 | 128927473.2453
|  |  |  | 62 | 2025-01-26 10:00 | 128927473.2453 | 1074395.6104 | -1700769.8641 | 127226703.3811
|  |  |  | 63 | 2025-02-25 20:00 | 127226703.3811 | 1060222.5282 | -1714942.9463 | 125511760.4348
|  |  |  | 64 | 2025-03-28 06:00 | 125511760.4348 | 1045931.337 | -1729234.1376 | 123782526.2972
|  |  |  | 65 | 2025-04-27 16:00 | 123782526.2972 | 1031521.0525 | -1743644.422 | 122038881.8752
|  |  |  | 66 | 2025-05-28 02:00 | 122038881.8752 | 1016990.6823 | -1758174.7922 | 120280707.083
|  |  |  | 67 | 2025-06-27 12:00 | 120280707.083 | 1002339.2257 | -1772826.2488 | 118507880.8341
|  |  |  | 68 | 2025-07-27 22:00 | 118507880.8341 | 987565.6736 | -1787599.8009 | 116720281.0332
|  |  |  | 69 | 2025-08-27 08:00 | 116720281.0332 | 972669.0086 | -1802496.4659 | 114917784.5673
|  |  |  | 70 | 2025-09-26 18:00 | 114917784.5673 | 957648.2047 | -1817517.2698 | 113100267.2975
|  |  |  | 71 | 2025-10-27 04:00 | 113100267.2975 | 942502.2275 | -1832663.247 | 111267604.0505
|  |  |  | 72 | 2025-11-26 14:00 | 111267604.0505 | 927230.0338 | -1847935.4408 | 109419668.6097
|  |  |  | 73 | 2025-12-27 | 109419668.6097 | 911830.5717 | -1863334.9028 | 107556333.707
|  |  |  | 74 | 2026-01-26 10:00 | 107556333.707 | 896302.7809 | -1878862.6936 | 105677471.0133
|  |  |  | 75 | 2026-02-25 20:00 | 105677471.0133 | 880645.5918 | -1894519.8827 | 103782951.1306
|  |  |  | 76 | 2026-03-28 06:00 | 103782951.1306 | 864857.9261 | -1910307.5484 | 101872643.5822
|  |  |  | 77 | 2026-04-27 16:00 | 101872643.5822 | 848938.6965 | -1926226.778 | 99946416.8042
|  |  |  | 78 | 2026-05-28 02:00 | 99946416.8042 | 832886.8067 | -1942278.6678 | 98004138.1364
|  |  |  | 79 | 2026-06-27 12:00 | 98004138.1364 | 816701.1511 | -1958464.3234 | 96045673.813
|  |  |  | 80 | 2026-07-27 22:00 | 96045673.813 | 800380.6151 | -1974784.8594 | 94070888.9536
|  |  |  | 81 | 2026-08-27 08:00 | 94070888.9536 | 783924.0746 | -1991241.3999 | 92079647.5537
|  |  |  | 82 | 2026-09-26 18:00 | 92079647.5537 | 767330.3963 | -2007835.0782 | 90071812.4754
|  |  |  | 83 | 2026-10-27 04:00 | 90071812.4754 | 750598.4373 | -2024567.0372 | 88047245.4382
|  |  |  | 84 | 2026-11-26 14:00 | 88047245.4382 | 733727.0453 | -2041438.4292 | 86005807.009
|  |  |  | 85 | 2026-12-27 | 86005807.009 | 716715.0584 | -2058450.4161 | 83947356.5929
|  |  |  | 86 | 2027-01-26 10:00 | 83947356.5929 | 699561.3049 | -2075604.1696 | 81871752.4233
|  |  |  | 87 | 2027-02-25 20:00 | 81871752.4233 | 682264.6035 | -2092900.871 | 79778851.5523
|  |  |  | 88 | 2027-03-28 06:00 | 79778851.5523 | 664823.7629 | -2110341.7116 | 77668509.8408
|  |  |  | 89 | 2027-04-27 16:00 | 77668509.8408 | 647237.582 | -2127927.8925 | 75540581.9483
|  |  |  | 90 | 2027-05-28 02:00 | 75540581.9483 | 629504.8496 | -2145660.6249 | 73394921.3233
|  |  |  | 91 | 2027-06-27 12:00 | 73394921.3233 | 611624.3444 | -2163541.1302 | 71231380.1931
|  |  |  | 92 | 2027-07-27 22:00 | 71231380.1931 | 593594.8349 | -2181570.6396 | 69049809.5536
|  |  |  | 93 | 2027-08-27 08:00 | 69049809.5536 | 575415.0796 | -2199750.3949 | 66850059.1587
|  |  |  | 94 | 2027-09-26 18:00 | 66850059.1587 | 557083.8263 | -2218081.6482 | 64631977.5105
|  |  |  | 95 | 2027-10-27 04:00 | 64631977.5105 | 538599.8126 | -2236565.6619 | 62395411.8485
|  |  |  | 96 | 2027-11-26 14:00 | 62395411.8485 | 519961.7654 | -2255203.7091 | 60140208.1394
|  |  |  | 97 | 2027-12-27 | 60140208.1394 | 501168.4012 | -2273997.0734 | 57866211.0661
|  |  |  | 98 | 2028-01-26 10:00 | 57866211.0661 | 482218.4256 | -2292947.049 | 55573264.0171
|  |  |  | 99 | 2028-02-25 20:00 | 55573264.0171 | 463110.5335 | -2312054.941 | 53261209.0761
|  |  |  | 100 | 2028-03-27 06:00 | 53261209.0761 | 443843.409 | -2331322.0655 | 50929887.0105
|  |  |  | 101 | 2028-04-26 16:00 | 50929887.0105 | 424415.7251 | -2350749.7494 | 48579137.2611
|  |  |  | 102 | 2028-05-27 02:00 | 48579137.2611 | 404826.1438 | -2370339.3307 | 46208797.9304
|  |  |  | 103 | 2028-06-26 12:00 | 46208797.9304 | 385073.3161 | -2390092.1584 | 43818705.772
|  |  |  | 104 | 2028-07-26 22:00 | 43818705.772 | 365155.8814 | -2410009.5931 | 41408696.1789
|  |  |  | 105 | 2028-08-26 08:00 | 41408696.1789 | 345072.4682 | -2430093.0064 | 38978603.1725
|  |  |  | 106 | 2028-09-25 18:00 | 38978603.1725 | 324821.6931 | -2450343.7814 | 36528259.3911
|  |  |  | 107 | 2028-10-26 04:00 | 36528259.3911 | 304402.1616 | -2470763.3129 | 34057496.0782
|  |  |  | 108 | 2028-11-25 14:00 | 34057496.0782 | 283812.4673 | -2491353.0072 | 31566143.071
|  |  |  | 109 | 2028-12-26 | 31566143.071 | 263051.1923 | -2512114.2823 | 29054028.7887
|  |  |  | 110 | 2029-01-25 10:00 | 29054028.7887 | 242116.9066 | -2533048.5679 | 26520980.2208
|  |  |  | 111 | 2029-02-24 20:00 | 26520980.2208 | 221008.1685 | -2554157.306 | 23966822.9148
|  |  |  | 112 | 2029-03-27 06:00 | 23966822.9148 | 199723.5243 | -2575441.9502 | 21391380.9646
|  |  |  | 113 | 2029-04-26 16:00 | 21391380.9646 | 178261.508 | -2596903.9665 | 18794476.9981
|  |  |  | 114 | 2029-05-27 02:00 | 18794476.9981 | 156620.6417 | -2618544.8329 | 16175932.1652
|  |  |  | 115 | 2029-06-26 12:00 | 16175932.1652 | 134799.4347 | -2640366.0398 | 13535566.1254
|  |  |  | 116 | 2029-07-26 22:00 | 13535566.1254 | 112796.3844 | -2662369.0901 | 10873197.0353
|  |  |  | 117 | 2029-08-26 08:00 | 10873197.0353 | 90609.9753 | -2684555.4992 | 8188641.5361
|  |  |  | 118 | 2029-09-25 18:00 | 8188641.5361 | 68238.6795 | -2706926.795 | 5481714.741
|  |  |  | 119 | 2029-10-26 04:00 | 5481714.741 | 45680.9562 | -2729484.5183 | 2752230.2227
|  |  |  | 120 | 2029-11-25 14:00 | 2752230.2227 | 22935.2519 | -2752230.2227 | -1.2917e-06
| 2010-01-31 | 2010-03-02 10:00 | 2010-04-01 20:00 | 2010-05-02 06:00 | 2010-06-01 16:00 | 2010-07-02 02:00 | 2010-08-01 12:00 | 2010-08-31 22:00 | 2010-10-01 08:00 | 2010-10-31 18:00 | 2010-12-01 04:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000
| 1900-01-29 10:00 | 1900-02-28 20:00 | 1900-03-31 06:00 | 1900-04-30 16:00 | 1900-05-31 02:00 | 1900-06-30 12:00 | 1900-07-30 22:00 | 1900-08-30 08:00 | 1900-09-29 18:00 | 1900-10-30 04:00 | 1900-11-29 14:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Date = [Date, row above]+F6
Interest payment = [Date]+F6
This is only an Example of schedule repayment with amortization table for 10 years at max of 10% interest per year with a 3 year grace period
Again this is only a demonstration that repayment is possible the actual interest will be determined during site visit.
Amortization table IBP Corp
Grace period
Amortization period

## Informe de compatibilidad
Informe de compatibilidad para Excel Fianacial Project for €300 Million Euros With Differant Interest Senarios To be used ready1111.xls
Ejecutar el 13/07/2010 11:00
Las siguientes características de este libro no son compatibles con versiones anteriores de Excel. Estas características podrían perderse o degradarse si guarda el libro con un formato de archivo anterior.
Pérdida menor de fidelidad | Nº de apariciones
Algunas celdas o estilos de este libro contienen un formato no admitido en el formato de archivo seleccionado. Estos formatos se convertirán al formato más cercano disponible. | 4